## HK Project List-27 Nov (New)
| Updated as at: 8 May 26 | [6 empty] | Intake Management | [6 empty] | Platform Expected Timeline | [7 empty] | Target Lauch
# | Project | Project Code | CI # | HK IT Lead | CD IT Lead | Program Lead/ PM | New Application (Y) / Project (N) | Request Submission to ETS | Estinated Ali Resource | ARB Review | IRM Review | ETS Review | Change Management | AliCloud DEV Approved | DEV | ETS Target Delivery (Provided by ETS) DEV | SIT | ETS Target Delivery (Provided by ETS) SIT | UAT | ETS Target Delivery (Provided by ETS) UAT | PROD /DR | ETS Target Delivery (Provided by ETS) PRD | Tech Launch | Business Go-Live | Update | Risk | Remarks | UAT Signoff Date | Provided PRD IP | ARB | AI | PII Data/PRD Data | FrontEnd in Azure? (yes/no) | Customer facing (Customer authentication)/Internet presence | AliCloud internet | Large number of internal users | Insurance agent facing (MCF Authentication)(Azure ADO) | UAT Readines for PRD Gol ive | GCS
1 | Quantum - JARVIS |  |  | Jerry | Darren Du | Janelle/ Cynthia | Y | Completed |  | Completed | Completed | Completed | Completed | Completed | 2025-07-15 | 2025-07-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-09-26 | 2025-09-26 | 2025-10-18 | 2025-11-02 | 13-Nov: Louis to send us CI to check if included for AliCloud
2 | Distribution Compensation System (DCS) revamp |  |  | Theresa | Lamar Wei | Janelle/ Kelvin | Y | Completed |  | Completed | Completed | Completed | Completed | Completed | 2025-07-15 | 2025-07-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-12-06 | 2025-09-26 | 2026-01-24 | 28-Jan-26 1/17/2026 | 5-Feb: DR will peform at 6-Feb 3 Feb: DCS DR drill on 6 Feb. Full backup starting 5:30pm. Drill target to start after 6pm - Monique/Gary. 29-Jan: 7-Feb or 14-Feb for DR 22-Jan: Container scan might have issue Sunny will provide BUSO report IRA report - Edison DB go live procedure -restore Db dump provided by vendor(required by Jeff) and program(by apps) access to PRD DB from DMS(via portable) to check data(access right should not download data)(DMS should not retreive DB)(This is just to read data only) 20-Jan: ETS-IRA: Vendor fixed docker image and IRA report is not fully approved(Go live plan: will raise issue and CAP esp Redhat) PII data for this release(pls get approval from Laura) Prisma scan Addtinal node for DCS is done 15-Jan: CSPM - 35 high issues to fix To fix all medium+ issue or else it cant be go live *if some medium got exception for 90 days, it will be good 13-Jan: DR design - to be discussed(Lamer\Theresa to provide PRD design)(2 days for ACK change for DCS) 2 Jan: DAST retest target 5 Jan. 23 Dec: UAT sign-off: target 23 Dec. CSPM testing can be initiated. 18 Dec: Pentest: No medium & higher issue found. UAT testing started. Target DR test: 17 Jan. 16-Dec: UAT starts pent test deployment issue in DEV env - resource shared with Jarvis and limited now (devops team is checking) 9-Dec: DAST scan is not yet completed Go Live date TBC 4-Dec: Schedule a DAST scanning in this afternoon(Lamer and will ask Firewall) 3-Dec: DAST server name or IP 2-Dec: DAST scanning could not be started now and working on the issue(Derek and Lamer) UAT testing start in next week Might postpone for 1 week 11-Jan or 17-Jan(To be confirmed with business) DB enquiry - AliCloud to RDS from laptop(required by Apps) 27-Nov: Request PRD vendor access on monitoring and logging (Aubrey to review) DB encryption can be enable by apps team(WIP) PostgreSQL - pgcrypto — cryptographic functions 25Nov: Vendor puts KMS on dev and testing. PRD support on db access - ODS (Lamer to discuss with Jeff) 20Nov: DR test review meeting(Sunny) 18-Nov: project schedule posptoned to 4-Jan. 28-Dec is the tech luanch. DR at 20-Dec(19-Dec signoff by business owner). SIT testing is in progress and UAT test will be started at 2-Dec. KMS issue is resolved(no major issue) SSL is still not resolved 13-Nov: Provided solution to vendor and how it will be hanlded with KMS(WIP)(Lamer)(ETA: TBC) 11-Nov: Under SIT and working on fixing issue(Theresa) Length of KMS and working with vendor on docker file to fix the issue(Lamar) DR for DCS might need downtime from Jarvis(Theresa) | SSL connection will need to enable(still testing) | move PRD From 12/13/2025 to 01/04/2026 Tech launch from 6-Dec to 28-Dec |  | CHG01285886 from: 21:00 24-Jan to 21:00 27-Jan |  | No | PII: No PRD: Yes |  | No |  | No | No | 1) Not signed UAT 2) Not fully THR\CSPM(depends on 1) | Approved
3 | IDP Solution |  |  | Jason Chan (Innovation) | Jakey Wu | Barry Cheung | Y | Completed |  | 2025-09-15 | Completed | Completed | Completed | Completed | 2025-09-15 | 2025-09-29 | 2025-09-30 | 2025-10-24 | 2025-10-15 | 2025-11-18 | 2025-10-15 | 2025-11-18 | 2026-01-16 | 2026-01-23 | 22-Jan: BUSO approval? IRA report 15-Jan: Tech Launach is tomorrow and is clean 13-Jan: UAT approval work is WIP No major risk 2 Jan: Complete DAST asap. 16-Dec: Runned DAST scan in 16-Dec and pass AI should be approved by this Friday(Jonah & Edward) After approved AI-VL on Friday, we can enable DEV,SIT, UAT on next Monday while THR on UAT 11-Dec: AI to submit evalation in this week Pent test at 2-Jan DAST scan at 15-Dec DR test can be planned within 30days after go live 9-Dec: ARB presented and approved VL(AI) approval is still in progress Qwen3-max on UAT 4-Dec: No ETA for AI approval(Jason - Jonah) No AI guardrail is required(Winnie\Sunny\Ken\Jamie - Issue and CAP) ARB Monday is to add Qwen3-Max(Joson) 3-Dec: Add Qwen3-max on ARB at 8-Dec AI Guardrail will review required or not at 4-Dec 2-Dec: UAT signoff at yesterday without AI test(conditional signoff without AI) 27-Nov: KMS working in UAT Rocket MQ is unstable(50% failure and 50% success)(Followup with Jakey\Jeff\Darren) AI approval(No update) AI protection(There is a test ) 25-Nov: KMS on UAT is working Rocket MQ is still not connected(WIP)(Alan can help to troubleshoot) LLM is still under approval(Jonah) 21-Nov: No update on Jonah and Edward on the status update on AI approval as it will affect UAT testing(Jason\Yeap) - No ADB is using on IDP(Jason to confirm with Jonah\AA)*ADB has embeedded AI - UAT testing KMS and Rocket MQ testing in progress e.g. firewall(Rabbit changes to Rocket) - For hardening, it will be CSPM 18-Nov: Under UAT testing. KMS firewall is still WIP(Jeff and Jason to work together) . Rabbit MQ access issue(Alibaba team to help for alternative way), New AI approval(Working with AA in this afternoon). Core service needs DR(ACK has active-active design in AliCloud - Jason prepares a DR test plan) 13-Nov qwen3-vl-plus, qwen-vl-max, qwen-vl-max-0813, qwen3-vl-plus-2025-09-23 required in AliCloud(Jakey and Jason confirms required)(These AI is not approved - Jason is working on approval with Roy/Jonah) to verify UAT env tomorrow and firewall is pending to open(Jakey) | - New AI not approved to use - qwen3-vl-plus, qwen-vl-max, qwen-vl-max-0813, qwen3-vl-plus-2025-09-23(AA and ADO team is working on approval) - AI protection |  | Conditional signoff at 1-Dec by Jason. - without AI as AI is not approved at this moment Decision - To confirm if we could proceed PRD setup and provide IP for firewall opening | CHG01280780 from 10:00 23-Jan to 23:00 23-Jan |  | Yes | PII: Yes PRD: Yes Data: AliCloud(MongoDB) |  | No |  | No | No | 1) Not signed UAT 2) Not fully THR\CSPM(depends on 1) 3) AI not approved | Approved
4 | NBUW/FUW (Future Underwriting Blueprint) ¦ GenAI Powered-up Underwriting (For AA Team) |  |  | Charles Ngo | Jeremy Wu/Bill Fu | Edward/John Pang | Y | Completed |  | 2025-10-13 |  |  |  |  | 2025-10-13 | 2025-11-07 | 2025-10-31 | 2025-11-07 | 2025-10-31 | 2025-11-22 | 2025-11-30 | 2025-12-15 | 2026-01-17 | 2026-01-25 | 22-Jan: BUSO approval? IRA report? 13-Jan: Tech launch at 17-Jan 23 Dec: E2E started. PROD env: Jeff to confirm. 18 Dec: UAT signed-off on 16 Dec. Proceed with PROD provision. 9-Dec: <no update> 4-Dec: - 27-Nov: Approved Embedded is enable 25-Nov: ADB approval is required on ADB-AI embedded(Every Monday on ARB meeting)(Harry\Jamie) 20-Nov: Jonah confirmed ADB-AI embedded is not on playbook and yet to confirm(Jonah\Charles) 18-Nov: Qwen 2.0 setup at UAT. ADB-AI model requests approval 13-Nov: qwen3-vl-plus, qwen-vl-max, qwen-vl-max-0813, qwen3-vl-plus-2025-09-23 are not required(Charles) Qwen3.0 is required only(Charles) ADB - AI search is required(Charles)(Jeremey is contact point of AA team)(To discuss with Sunny) 11-Nov: UAT: ADB & ADBAI part, we don't have security approval for it. Need Yunnie Yin approval for this into UAT & PRD *Cloud Flow will be ready at AliCloud-HK at 20-Nov | ADB with embedded and revamped Qwen-3 and medical(DEV\SIT , apps can enable AI embedded) | New AI not approved to use - qwen3-vl-plus, qwen-vl-max, qwen-vl-max-0813, qwen3-vl-plus-2025-09-23(Apps team is working on approval) ] - not required |  | CHG01286225 from 00:00 25-Jan to 10:00 25-Jan |  | Yes | PII: No PRD: Yes Data: AliCloud(ADB) |  | No |  | Yes | Yes | 1) Not signed UAT 2) Not fully THR\CSPM(depends on 1) 3) AI not approved | Approved
5 | NBUW/FUW (Future Underwriting Blueprint) ¦ One Single View NBUW Platform |  |  | Charles Ngo | Jenny He / Aden | Edward/ Cayden | Y | 2025-07-30 |  | 01-Sep-25 (SDR2) | Completed | Completed | Completed | Completed | 2025-09-15 | 2025-10-21 | 2025-10-31 | 2025-10-30 | 2025-10-31 | 2025-11-10 | 2025-11-30 | 2025-12-15 | 2025-11-02 | 2026-01-03 | 2 Jan: To confirm PROD env & post-implementation scheduled 9pm-3 Jan. 23 Dec: All test completed. PROD env ready. Waiting for CAP confirmation. 18 Dec: DR test: 17 Jan. Tech launched. All scans completed. 16-Dec: Cloudflow has THR completed APPS-IRA-Signoff is WIP(includes Code, DAST, Pent Test) GCS signoff? 11-Dec: Qualys is done Appsscan is done CSPM/THR is done DLP: update 9-Dec: To provide PRD IP 4-Dec: UAT is on track 3-Dec: target to have UAT on Monday Go live data to be cofirmed 27-Nov: CloudFlow is enable(WIP) 25-Nov: CloudFlow did the hardening and waiting for IRA to confirm to release 20-Nov: Cloud flow is setup at HK and setup at DEV waiting IRA to review 18-Nov: Waiting for Cloud flow(To confirm Dongmei approval first before 20-Nov) 13-Nov: Cloud flow should be ready at 20-Nov and ETS ready at 26-Nov Tech launch at 2-Nov without cloudflow at PRD now(no AliCloud) 6 Nov: Exception will be secured for 3 Jan '26 Go-Live. Sep: engaged ETS and Ali in Q2 (before excel kicks-in); excel request submit date: 30-Jul-26. | Cloudflow is not ready at AliCloud HK until 20-Nov Go Live date at 3-Jan(change freeze) | 10 Nov: CloudFlow SG 20 Nov: CloudFlow HK will be available & target service enable in FUW UAT on 27 Nov. | Signoff of final apps release at 8-Dec by Charles Ngo | WIP |  | No | PII: No PRD: Yes Log: Yes Data: Azure |  | No |  | Yes | No | 1) Not signed UAT 2) Not fully THR\CSPM(depends on 1) | Approved
6.1 | Replatform Marketing Campaign System (Leads Generation) - LEAD |  |  | Vincent Kong (LEAD) | Cade Deng | Janelle/ Bowie Lee | Y | 2025-09-17 |  | 2025-07-21 |  |  |  |  | 2025-10-13 | 2025-10-21 | 2025-10-21 | 2025-10-21 | 2025-11-20 | 2025-11-20 | 2025-12-15 | 2025-12-15 | 2025-12-18 | 2026-01-04 | 23 Dec: Tech-launch completed. 18-Dec: Tech-launch tonight. Status: Good. DR test: 17 Jan. 16-Dec: Tech launch will release 1 service and Business will releae the rest 3 service APPS-IRA-Signoff is WIP(includes Code, DAST, Pent Test) No code change between tech launch and businees launch. THR on PRD(WIP - ETA: today) 9-Dec: Firewall ticket for PRD submitted. Qualys and CSPM is WIP on UAT?(To confirm with Jeff) DAST scan is on this week(need to scan by server) Pent test by PH(via jump host) 4-Dec: WIP 3-Dec: No AI and no PII data(Trista, pls confirm) Apps release signoff and can proceed for PRD setup which IP could be provided for firewall opening(DB IP to provide first) DAST scanning is having issue 27-Nov: Fixed timeout issue Firewall will enable today for ingress(will plan for UAT test tomorrow) PRD firewall is plan to submit earlier(UAT signoff date is planned 25-Dec) 25-Nov: Configure KMS in UAT and SIT but having timeout issue(Cade to work with Jeff team)(UAT signoff is on 20-Nov: Firewall submitted on UAT on Thursday. AAD is progress 18-Nov: <Not joined> 13-Nov: DEV is just deployed and will start test. UAT pending firewall(Cade) 3-Jan is change freeze and no change of go live date(Cade) to work through solution with Sunny(Cade) 11-Nov: Under DEV and SIT testing(Trista) To know the IPs of PRD before 7-Dec(for firewall) | Go Live date at 3-Jan(change freeze) |  | Signoff of final apps release at 2-Dec by Cade | Yes |  | No | PII: No PRD: Yes |  | No |  |  |  |  | Approved
6.2 | Replatform Marketing Campaign System (Leads Generation) - Replatform |  |  | Albert/Trista (replatform) | Cade Deng | Janelle/ Bowie Lee | N 6.1 | 2025-09-17 |  | 2025-07-21 |  |  |  |  | 2025-10-13 | 2025-10-21 | 2025-10-21 | 2025-10-21 | 2025-11-20 | 2025-11-20 | 2025-12-15 | 2025-12-15 | 2026-01-04 | 2026-02-13 | 12-Feb: GCS no concern, ETS IRA is approved 5-Feb: GCS form to submit by Sunny will send out in next week 3 Feb: Proposed to bring forward 13 Feb. 29-Jan : No PII and internet facing 22-Jan: BUSO approval? IRA report? 18-Dec: Tech-launch tonight. Status: Good. DR test: 17 Jan. 16-Dec: Tech launch will release 1 service and Business will releae the rest 3 service APPS-IRA-Signoff is WIP(includes Code, DAST, Pent Test) No code change between tech launch and businees launch. THR on PRD(WIP - ETA: today) 9-Dec: Firewall ticket for PRD submitted. Qualys and CSPM is WIP on UAT?(To confirm with Jeff) DAST scan is on this week(need to scan by server) Pent test by PH(via jump host) 4-Dec: WIP 3-Dec: No AI and no PII data(Trista, pls confirm) Apps release signoff and can proceed for PRD setup which IP could be provided for firewall opening(DB IP to provide first) DAST scanning is having issue 27-Nov: Fixed timeout issue Firewall will enable today for ingress(will plan for UAT test tomorrow) PRD firewall is plan to submit earlier(UAT signoff date is planned 25-Dec) 25-Nov: Configure KMS in UAT and SIT but having timeout issue(Cade to work with Jeff team)(UAT signoff is on 20-Nov: Firewall submitted on UAT on Thursday. AAD is progress 18-Nov: <Not joined> 13-Nov: DEV is just deployed and will start test. UAT pending firewall(Cade) 3-Jan is change freeze and no change of go live date(Cade) to work through solution with Sunny(Cade) 11-Nov: Under DEV and SIT testing(Trista) To know the IPs of PRD before 7-Dec(for firewall) | Go Live date at 3-Jan(change freeze) |  | Signoff of final apps release at 2-Dec by Cade | Yes |  | No | PII: No PRD: Yes |  | No |  | No | No | 1) Not signed UAT 2) Not fully THR\CSPM(depends on 1) | Not Submissed
7 | Agency Room Booking System |  |  | Tony Lin/Richard/Albert | Michael Mei | Carol Teoh | Y | 2025-09-17 |  | 2025-09-29 | WIP |  |  |  | 2025-10-13 | 2025-10-21 | 2025-10-27 | 2025-10-21 | 2025-10-27 | 2025-11-07 | 2025-11-30 | 2025-11-30 | 2025-12-22 | 2026-01-04 | 20-jan: RPO/RTO - data replication is longer but still within RPO/RTO 15-Jan: DR will perform on this Saturday 13-Jan: design document - active-active on ACKS and DB(Xin Tong and Tony) 23 Dec: Tech-launch completed. Manutouch integration to Ali to be raised on 4 Jan. 18 Dec: Pentest: No medium & above issues. Final report 22 Dcc. Tech launch: 22 Dec night. Status: Good. DR test: 17 Jan. 16-Dec: THR is completed on UAT Pent test is targeted to completed by 17-Dec Apps monitoring and logging are WIP APPS-IRA-Signoff is WIP(includes Code, DAST, Pent Test) 11-Dec: MFC testing is fine and MVC center is not fine(Checking firewall) Plan to have tech launch at 20-Dec DAST scan is completed and no medium or above UAT signoff -17-Dec 9-Dec DAST scan to scan Pen test to scan 4-Dec: Pent test is WIP UAT signoff is 4-Dec 3-Dec: <Not joined> 27-Nov: Pen test 1-Dec and 19-Dec UAT is still in progress 25-Nov: UAT env need permission to setup token(Aubrey) Firewall will need to open for authenication(Yoyo) 20-Nov: UAT is setting up with ADO and target testing in next week. Penetration test is arranged in next week. scanning of source code is required to vendor(TBC) 18-Nov: Penetration test is not confirmed. DEV is in progress and no issue. UAT will start next week 13-Nov: Start testing on DEV. Next week will have new release from vendor(Tony) 4-Jan is still the go live date(Tony) 11-Nov: Not started yet on DEV | Go Live date at 3-Jan(change freeze) |  | Signoff of final apps release at 4-Dec by Albert | Yes |  | No | PII: No PRD: No |  | No |  | No | Yes | 1) Not signed UAT 2) Not fully THR\CSPM(depends on 1) | Approved
8 | Quantum LeadGen by MarTech CP 2 |  |  | Albert Ahg |  | Janelle/ Bowie Lee | Y | Not Started |  | Target 10 Nov |  |  |  |  | 2025-10-13 | 2025-10-21 | 2025-10-21 | 2025-10-21 | 2025-11-20 | 2025-11-20 | 2025-12-15 | 2025-12-15 | 2025-12-18 | 2026-01-04
9 | ATAS(non HK) |  |  |  | Jace | Raina |  | Yes |  | 2025-12-01 |  |  |  | Yes | 2025-10-21: Y; 2025-11-20: 2025-11-17; 2025-12-15: Y; 2025-12-18: 2025-12-09; 2026-01-04: 2026-04-13 | UAT testing now(ETA:3-Dec to completed UAT testing) | Max Compute and Data Work |  | Signoff of final apps release at 1-Dec by Raina | Yes |  | N | Y |  | N |  | No | No |  | Approved
10 | Data Quality and Governance Transformation (ODS) | 29919 |  | Terence Leung Micheal Cheng | Sourav / Ranjith | Yeap/ Gary |  | 2025-09-17 |  | 2025-09-29 |  |  |  | Yes | 2025-10-13 | 2025-10-21 | 2025-10-13 | 2025-10-21 | 2025-10-31 | 2025-11-07 | 2025-11-11 | 2025-11-17 | 30-Mar-26 20-Mar-26 | 30-Mar-26 6-Jun-26 | 8-Apr: Tech launched on 20 Mar. Target: - 30 Apr: production data ingestion into PROD - 31 Mar: go-live 12-Feb: Tech launch at 28-Feb. Go Live to be confirmed 29-Jan: It should be all data for HKIT. what is this phase for? e.g. data injection? 23 Dec: Flink THR to be updated by Jeff. 18 Dec: Testing is UAT proceeding. 16-dec: UAT testing conducting and cannot access to UAT 11-Dec: UAT account is requestd 9-Dec: To setup UAT env by ETS(ETA: To be confirmed by Jeff) 4-Dec: review UAT schedule and work 3-Dec: will review the timeline based on UAT release schedule 27-Nov: Flink is enabled and working on testing(Internal DNS resolution for Flink only) 25-Nov: Flink will need to open and under IRA review(Edison) 20-Nov: On track and go to SIT after DEV 18-Nov: <Sourav><Ranjith> testing in dev(ETA:25-Nov). to add Flink and datawork on DEV Jeff comments in purple Potential Risk for Dataworks to go live (THR) - New Product Flink required 13-Nov: Under Dev testing (Sourav) Add Flink is approved by HK ARB(Harry to provide pattern to use)(To confirm setup time after Harry) Some is on UAT already - Data work is also required(Jeff) | Flink(new service) and Data Work |  |  |  |  | N | PII: Yes PRD: Yes Data: Gamma DC |  | N | N | No | No | 1) Not signed UAT 2) Not fully THR\CSPM(depends on 1) | Not Submissed
11.1 | CAS modernization: PolarDB | 27473 |  | Wilson/Ka Fai | Sammi Wan | Yeap/ Gary |  | 2025-09-17 |  | 29-Sep-25 (SDR 3) |  |  |  | Yes | 2025-10-25 | 2025-10-24 | 2025-11-25 | 2025-10-28 | 2025-11-25 | 2025-11-28 | 2026-04-06 | 2026-01-02 | 2026-11-28 | TBC(Nov) | 5-Feb: To send out risk report on next Wed 29-Jan: Target to have PII data at end of Feb (28-Feb with dat sync to AliCloud) |  |  |  |  | Y | N | Y | N | N | N | N | N |  | Not Submissed
11.2 | CAS modernization: Data ingestion into production CAS PolarDB | 27473 |  | Wilson/Ka Fai | Sammi Wan | Yeap/ Gary |  | 2025-09-17 |  | 29-Sep-25 (SDR 3) |  |  |  |  | Completed | N/A | Completed | N/A | 2026-04-13 | N/A | 2026-04-30 | N/A | 2026-04-30 | N/A | 8-Apr: Target production data to be ingested on 30 Apr. Current loading into UAT. |  |  |  |  | Y | N | Y | N | N | N | N | N
11.3 | CAS modernization: CAS forms & reports | 27473 |  | Mabel/Ka Fai | Sammi Wan | Yeap/ Gary | [8 empty] | 2025-10-13: 2026-04-20; 2025-10-21: 2026-04-20; 2025-11-20: 2026-05-15; 2025-12-15: 2026-07-10; 2025-12-18: 2026-11-28
11.4 | CAS modernization: CA batch-job | 27473 |  | Wilson/Ka Fai | Sammi Wan | Yeap/ Gary | [8 empty] | 2025-10-13: 2026-04-20; 2025-10-21: 2026-04-20; 2025-11-20: 2026-05-15; 2025-12-15: 2026-07-10; 2025-12-18: 2026-11-28 | 8-Apr: ECS env required for CA batch job.
12 | FUW (Future Underwriting Blueprint) ¦ Digital Submission Enhancement (ePOS)(FUW Pillar 5) |  |  | Frederick Tsui | Jenny He | Edward/ Kin Chan |  | 2025-09-17 |  | 01-Sep-25 (SDR1) |  |  |  | Yes | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-02-01 | 2026-02-15 | 2026-02-15 | 2026-03-15 | 2026-03-15 | 1-Apr-26 19-Apr-26 | 1-Apr-26 19-Apr-26 | 23-Mar: Service call to Ali AI Search (approved component) & no env required. Should not be started depends on 4) and 5) |  |  |  |  | Y | N | Y | Y | Y | N | N | N | Y | Not Submissed
13 | COSMOS (DCS) Phase 2 |  |  | Theresa Cheung | Lamar Wei | Janelle/ Stephen Ho |  | 2025-09-17 |  | 2025-09-01 |  |  |  |  | 20-Oct-25 1-Aug-26 4-May-26 |  | 20-Oct-25 1-Aug-26 4-May-26 |  | 15-Jan-26 1-Dec-26 6-Jul-26 |  | 15-Feb-26 1-Feb-27 26-Oct-26 |  | 15-Mar-26 5-Dec-26 | 20-Jul-26 1-Mar-27 23-1-27 | 3 Feb: RCS by end-Feb & build Distribution ODS.
14 | Universal Life (previously known as IUL) |  |  | George Lau |  | Jess Wong | N | 2025-11-27 |  | 2025-11-24 |  |  |  |  | 15-Dec-25 2-Feb-26 |  | 15-Dec-25 2-Feb-26 |  | 2026-03-15 |  | 2026-02-02 |  | 2026-05-04 | 5/17/2026 TBC | 30-Mar: Reschedule/Put on-hold. |  | No Ali env requirements as this is a product project.
15.1 | NBUW/FUW (Future Underwriting Blueprint) ¦ One Single View NBUW Platform Phase 2 - Apr release: application enhancement - Jul release: Tech-Launch on Ali migration for OSP |  |  | Charles Ngo | Jenny He / Aden | Edward/ Cayden | N | 2026-03-09 |  | 01-Sep-25 (SDR2) | Completed | Completed | Completed | Yes | 2026-04-06 | Y | 2026-04-06 |  | 2026-05-11 |  | 2026-06-19 |  | 2026-07-19 | 2026-11-08 | 27-Mar: Phase 2 enhancement will be launched on-top of Phase 1 (#5) launched on 3 Jan earlier. 16-Mar: Event Bridge has been flagged as "Y" under #4 and #5 |  |  |  |  | Y | N | Y | N | N | N | Y (~2XX) | N
15.2 | NBUW/FUW (Future Underwriting Blueprint) ¦ GenAI Powered-up Underwriting (For AA Team) - Apr release: application enhancement - July release: application enhancement + integration with OSP |  |  | Charles Ngo | Jeremy Wu/ Plato Leung | Edward/John Pang | N | Completed |  | 2025-10-13 |  |  |  | Yes | 2026-03-16 | Y | 2026-04-30 |  | 2026-05-29 |  | 2026-07-19 |  | 2026-07-19 | 2026-11-08 | [5 empty] | Y | Y | N | N | N | N | N | N
16 | GI partnership |  |  | Eric Wong |  | Kin Chan | Y | Not Started |  | 2025-11-24 |  |  |  | Yes | 2026-03-15 | Y | 2026-03-15 |  | 2026-05-01 |  | 2026-06-15 |  | 2026-07-20 | 2026-07-20 | [5 empty] | Y | N | N | N | Y |  | Y | Y
17 | MCF |  |  | Pong Soon Lung | Ronaldo Wang |  | N | Not Started |  | TBC |  |  |  | Yes | 31-Mar-26 1-Jul-26 | Y | 31-Mar-26 1-Jul-26 |  | 2026-07-15 |  | 2026-07-31 |  | 2026-07-31 | 2026-07-31 | [6 empty] | N | N | Y | Y |  | N | Y
18 | Agency Printing |  |  | Joseph Wong | Serena Wang | TBC | N | Not Started |  | TBC |  |  |  |  | 1-Apr-26 N/A |  | 1-Apr-26 N/A |  | 15-May-26 2-Jul-26 |  | 15-Jun-26 1-Sep-26 |  | 15-Jul-26 1-Oct-26 | 15-Jul-26 1-Nov-26 | 7-May: Vendor solution. 26-Mar: ECS env requirement. 24-Feb: Microsoft SQL is required(PGC code). What is DR requirement? 29-Jan: Internet facing , agency network, dmz zone for agency, agency domain
19 | MOVE 2.0 |  |  | Albert Ahg/Kwok Shing Lee |  | Janelle/Williams Tan | N | Not Started |  | Target 10 Nov |  |  |  |  | 15-Feb-26 8-Jun-26 |  | 15-Feb-26 8-Jun-26 |  | 1-Jul-26 |  | 2026-09-01 |  | 2026-11-08 | 2027-01-10 | [5 empty] | Y | N |  | Y | Y | N | Y | N
20 | Sky (to utilize Move 2.0 env) | 31152 |  | Albert Ahg/Axel Leung |  | James Cheung/Eva Law | Y | Not Started |  | James |  |  |  |  | N/A |  | N/A |  | 2026-03-15 |  | 2026-09-01 |  | 2026-12-28 | 2027-02-01 | [5 empty] | Y | N |  | Y | Y | N | Y | N
21.1 | ICHS (CTOM) - Claims ODS | 30659 |  | Vincent Lee | Neil Li | Ellen Gail Gu/Barry L. | Y | Not Started |  | Target 10 Nov |  |  |  |  | 2026-03-01 |  | 2026-03-01 |  | 2026-06-15 |  | 2026-07-06 |  | 2026-07-19 | 7-Nov-26
21.2 | ICHS (CTOM) | 30659 |  | Vincent Lee | Neil Li | Ellen Gail Gu/Barry L. | Y | 1-Mar-26 6-Jul-26 |  | 1-Mar-26 6-Jul-26 |  | 2026-06-15 |  | 2026-06-30 | 2026-06-15 |  | 2026-06-15 |  | 2026-09-01 |  | 2026-10-26 |  | 7-Nov-26 | 7-Nov-26
22 | Onboarding Journey Digitalization & Back Office Automation (No AliCloud env requirement) |  | CI00005294596 | Tammy Tam/Ben Fong/Helen Kwong | Jessica Li | Bowie Lee | N | [7 empty] | N/A |  | N/A |  | N/A |  | N/A |  | N/A | 19-Jul-2026 5-Nov-2026 3-Jan-2027 | No Ali env required as application is writing data into Distribution ODS. |  |  |  |  | Y | No | Y | Y | No | N | Y | Yes
23 | Project Quantum – Agency Comp Review (No AliCloud env requirement) |  |  | Tony Lee Theresa Cheung |  | Stephen Ho | N
24 | Project Quantum – Leads Mgmt (No AliCloud env requirement) | 30748 |  | Vincent Kong |  | Queenie | N
25 | Project Quantum – AgencyBI (No AliCloud env requirement) | 30747 | CI00000087554 | Tammy Tam | Void Zheng | Queenie | [8 empty] | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A | Agency BI still in Azure, enhancement doing this year |  |  |  |  | Y | No | N | Y | No | N | No | Yes
26 | Project Quantum – Project Management (No AliCloud env requirement) |  |  |  |  | Janelle
27 | Single Customer App (No AliCloud env requirement) |  |  |  |  | Almira Leung
28 | Project Sky (Duplicate) | 31152 |  | Axel Leung |  | Queenie | [17 empty] | 2027-01-02
29 | Digital Payment Transformation |  |  |  |  | Carol Teoh | N
30 | MCV Operations Enhancement in Buy Journey |  |  |  |  | Carol Teoh | N
31 | IA Commission Spreading (No AliCloud env requirement) |  |  | George Lau |  | Jess Wong
32 | Policy Services Enhancement (No AliCloud env requirement) | 31269 |  | Elvis Lee | Vera Liu | Eva Mei Ling Lau | N | [15 empty] | 2026-07-19 | Jan 2029 (TBC) | 3 phases of this project: July 2026 release - 3rd Party Payment Nov 2026 release - Oversea Payment Jan 2027 - Designated Requester Provided dates (listed in left hand side) are for July 2026 release, the other 2 phases planning TBC
33 | Distribution Health Enablement (Agency)
34 | Simplified Chinese / "Project Jianhua / 简化" (No AliCloud env requirement) |  |  |  |  | Alice Zhou | N | [7 empty] | 1-Jue |  | 1-Jue |  | 2026-09-01 |  | 2026-10-01 |  | NA | 2026-11-08
35 | Orion - Goup Health System Replacement (GLH) |  |  | Judith / Eric Wong |  | Minshan Zhang/ Chee King Poon | Y | [7 empty] | 2026-07-01 |  | 2026-07-01 |  | 2026-08-01 |  | 2026-09-01 |  | 2026-09-01 | 2026-11-07 | 26 Mar: GLH's Nov stage 3 milestone is to interface to ODS-Polar (Policy, Product & Customer)
36 | Project Glider - reinsurance implementation (No AliCloud env requirement) | 31249 |  |  |  | Queenie | N | [7 empty] | N/A |  | N/A |  | N/A |  | N/A |  | N/A | N/A
37 | TD MVA | [5 empty] | N
38 | AML Replacement | [5 empty] | N
39 | HKPLA (completed project） |  |  |  |  | Queenie | N | [17 empty] | Completed
40 | Immediate Annuity（to be complete in Jul 2026 ） |  |  |  |  | Iris Vong | N
41 | Product Onboarding Acceleration​ |  |  |  |  | Marklee Hu | Y | [7 empty] | 2026-05-29 |  | 2026-06-05 |  | 2026-06-26 |  | N/A |  | 2026-06-26 | 2026-07-31
42 | Nexus |  |  | Albert / Axel |  | Chee Kin Poon | Checking | [22 empty] | N | N | TBC | Y | Y | Y | N | N
| INFOR(non HK) | [8 empty] | TBC |  |  |  | Yes | [9 empty] | 2026-10-01
| Additional item |  |  | Requirement |  | Owner
| Global year-end Change Freeze Cycle will start Wednesday December 24th, 2025, at 12:00pm (noon) EST/HKT until Thursday January 8th, 2026, at 11:59am EST/HKT. |  |  | If go live between change freeze. 1) HK team will need to raise and get ECR approved for any change required(ETS will not raise any ECR), 2) Any change required on 3-Jan will need well plan as Azure change might not have global team to perform the work |  | HK Apps Owner
| New AI Service |  |  | Apps owner will need to get approval on AI at AliCloud i)Use case or Prompt Enginnering(ADO & AA) ii) Foundation LLM Evaluation(Eugene Wen, Global Data Technology ) |  | Apps Owner, ADO, AA, GD
| New Service(Non AI) |  |  | ETS-IRA and BU-IRA will need to approve before enable at AliCloud(Same as Azure) |  | ETS-IRA and BU-IRA
| Other projects timeline |  |  | To provide\revise the timeline |  | Yeap
| No ECS (VM) should be created |  |  | VM creation requires approval |  | Harry

## Inflight Project
No | Date | Item | Details | Raised By | Go Live
1 | 2025-07-30 | Jarvis | Event Bridge | Ka Fai / Kenneth | 2025-11-01
2 | 2025-07-30 | DCS | Function Compute | Ka Fai / Kenneth | 2025-11-01

## (old)HK Project List-9 Oct(R2)
| Updated as at: 9 OCT |  |  |  |  | Intake Management | [5 empty] | Platform Expected Timeline | [7 empty] | Target Lauch
# | Project | Project | HK IT Lead | CD IT Lead | Program Lead/ PM | Request Submission to ETS | ARB Review | IRM Review | ETS Review | Change Management | AliCloud DEV Approved | DEV | ETS Target Delivery (Provided by ETS) DEV | SIT | ETS Target Delivery (Provided by ETS) SIT | UAT | ETS Target Delivery (Provided by ETS) UAT | Pre-PROD/PROD/DR | ETS Target Delivery (Provided by ETS) PRD | Tech | Business Go-Live | Status | Today | Yesterday
1 | Quantum - JARVIS | Quantum - JARVIS | Jerry | Darren Du | Janelle/ Cynthia | Completed | Completed | Completed | Completed | Completed | Completed | 2025-07-15 | 2025-07-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-09-26 | 2025-09-26 | 2025-10-18 | 2025-11-02 | Completed | Qwen 3.0 Apps IRA approval(Done) Pentration Test(Conducted) Jonah use case review
2 | Distribution Compensation System (DCS) revamp | Distribution Compensation System (DCS) revamp | Theresa | Lamar Wei | Janelle/ Kelvin | Completed | Completed | Completed | Completed | Completed | Completed | 2025-07-15 | 2025-07-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-09-26 | 2025-09-26 | 2025-11-29 | 2025-12-13 | Back to UAT(17-Nov,startes and 5 Signoff) under SIT testing DB SSL issue - Content is too long to push from KMS(max size limit?)(resolution: connect to OSS mount as local file? or to find where 3 for HK only) Issue: CPU resource changes for PaaS Remediation: Confirmed with HK-Architecture, no change on platform | 7-Dec(morning) should schedule DR - Sunny to discuss with Jarvis on maintenance window(Deploy code to PRD before DR test -Theresa)
3 | IDP Solution | IDP Solution | Jason Chan (Innovation) | Jakey Wu | Anurag/ Alice | Completed | 2025-09-15 | Completed | Completed | Completed | Completed | 2025-09-15 | 2025-09-29 | 2025-09-30 | 2025-10-24 | 2025-10-15 | 2025-11-18 | 2025-10-15 | 2025-11-18 | 2026-01-15 | 2026-01-22 | Under SIT Testing Adding component - Change to RabbitMQ | Revised PRD launch at 22-Jan. To review PRD timeline(Jakey)
4 | NBUW/FUW (Future Underwriting Blueprint) ¦ GenAI Powered-up Underwriting (For AA Team) | NBUW/FUW (Future Underwriting Blueprint) ¦ GenAI Powered-up Underwriting (For AA Team) | Charles Ngo | Jeremy Wu/Bill Fu | Edward/ Edward | Completed | 2025-10-13 |  |  |  |  | 2025-10-13 | 2025-11-13 | 2025-10-31 |  | 2025-10-31 |  | 2025-11-30 | 2025-12-15 | N/A | 2026-01-03 | Under DEV: Enable AnalyticDB for testing at 4-Nov Adding component - AI on ADB | Completed
5 | NBUW/FUW (Future Underwriting Blueprint) ¦ One Single View NBUW Platform | NBUW/FUW (Future Underwriting Blueprint) ¦ One Single View NBUW Platform | Charles Ngo | Jenny He / Aden | Edward/ Cayden | 2025-07-30 | 01-Sep-25 (SDR2) | Completed | Completed | Completed | Completed | 2025-09-15 | 2025-10-21 | 2025-10-31 | 2025-10-30 | 2025-10-31 | 2025-11-10 | 2025-11-30 | 2025-12-15 | 2025-11-02 | 2025-01-03 | <API call only, no work> | engaged ETS and Ali in Q2 (before excel kicks-in); excel request submit date: 30-Jul-26
6 | FUW (Future Underwriting Blueprint) ¦ Digital Submission Enhancement (ePOS) | FUW (Future Underwriting Blueprint) ¦ Digital Submission Enhancement (ePOS) | Frederick Tsui | Jenny He | Edward/ Flora | 2025-09-17 | 01-Sep-25 (SDR1) |  |  |  |  | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-02-01 | 2026-02-15 | 2026-02-15 | 2026-03-15 | 2026-03-15 | 2026-04-01 | 2026-04-01 | <API call only, no work>
7 | Replatform Marketing Campaign System (Leads Generation) | Replatform Marketing Campaign System (Leads Generation) | Albert | Cade Deng | Janelle/ Bowie Lee | 2025-09-17 | 2025-07-21 |  |  |  |  | 2025-10-13 | 2025-10-21 | 2025-10-21 | 2025-10-21 | 2025-11-20 | 2025-11-20 | 2025-12-15 | 2025-12-15 | N/A | 2026-01-03 |  | 8-Jan is change freeze end time
8 | Agency Room Booking System | Agency Room Booking System | Tony Lin/Richard/Albert | Michael Mei | Carol Teoh | 2025-09-17 | 2025-09-29 | WIP |  |  |  | 2025-10-13 | 2025-10-21 | 2025-10-27 | 2025-10-21 | 2025-10-27 | 2025-11-07 | 2025-11-30 | 2025-11-30 | N/A | 2026-01-04 |  | Pending decision if Alibaba timeline feasible
9 | Data Quality and Governance Transformation (ODS) | Data Quality and Governance Transformation (ODS) | Terence Leung Micheal Cheng | Scott Li | Yeap/ Gary | 2025-09-17 | 2025-09-29 |  |  |  |  | 2025-10-13 | 2025-10-21 | 2025-10-13 | 2025-10-21 | 2025-10-31 | 2025-11-07 | 2025-11-11 | 2025-11-17 | N/A | 2025-12-31 | To confirm application requirement. Container registry could not be used. | Jeff comments in purple Potential Risk for Dataworks to go live (THR) - New Product
10 | CAS modernization | CAS modernization | Wilson/Ka Fai | Sammi Wan | Yeap/ Gary | 2025-09-17 | 29-Sep-25 (SDR 3) |  |  |  |  | 2025-10-25 | 2025-10-24 | 2025-11-25 | 2025-10-28 | 2025-11-25 | 2025-11-28 | 2026-01-02 | 2026-01-02 | N/A | 2025-11-25 |  | Phase 1 data sync is at Nov. Go Live at June-2025
11 | DCS: Phase 2 | DCS: Phase 3 | Theresa Cheung | Lamar Wei | Janell/ Kelvin Mak | 2025-09-17 | 2025-09-01 |  |  |  |  | 2025-10-20 | 2025-10-29 | 2025-12-15 | 2025-12-15 | 2026-01-15 | 2026-01-15 | 2026-02-15 | 2026-02-15 | 2026-03-15 | 2026-07-20 | Issue: SSL on DB connection is required DEV is waiting to setup as SSL issue as data is transferred from Postgress DB to Polar DB(Ali to Ali)(using RSF\RCF for deploy) | Shared ARB desk Go without SSL
12 | MCF | MCF | Pong Soon Lung | Ronaldo Wang | [7 empty] | 2025-10-25 | 2025-12-15 |  | 2026-01-15 |  | 2026-02-15 |  | 2026-03-15 | TBC | TBC
13 | CTOM | CTOM | Vincent Lee | Neil Li | Anurag/ Gail |  | 29-Sep-25 (SDR 1) |  |  |  |  | 2026-01-15 | 2026-01-15 |  | 2026-02-15 | 2026-02-15 | 2026-03-15 | 2026-03-15 | 2026-04-15 |  | 2026-06-01
14 | Agency printing | Agency printing | Joseph Wong |  | Yeap | [6 empty] | 2026-01-05 | 2026-01-05 |  | 2026-02-15 | 2026-02-01 | 2026-03-15 | 2026-03-01 | 2026-04-15 |  | 2026-03-26
15 | GLH (Orion) | GLH (Orion) | Judith / Eric Wong |  | Anurag/ TBC | [6 empty] | 2026-01-15 | 2026-01-15 |  | 2026-02-15 | 2026-02-15 | 2026-03-15 | 2026-03-15 | 2026-04-15 |  | 2026-06-01
16 | MOVE 2.0 | MOVE 2.1 | Albert |  | Emily/ TBC |  | Target 10 Nov |  |  |  |  | 2026-01-05 | 2026-01-05 |  | 2026-02-15 | Q1-26 | 2026-03-15 | 2027-01-03 | 2026-04-15 | TBC | TBC
17 | Sky | Sky | Albert |  |  |  | James |  |  |  |  | 2026-01-05 | 2026-01-05 |  | 2026-02-15 | Q1-26 | 2026-03-15 | 2027-01-03 | 2026-04-15 | TBC | TBC
18 | Quantum LeadGen by MarTech CP 2 | Quantum LeadGen by MarTech CP 3 | Albert Ahg |  | Janelle/ Bowie Lee |  | Target 10 Nov |  |  |  |  | 2026-01-05 | 2026-01-05 |  | 2026-02-15 | Q1-26 | 2026-03-15 | 2026-07-19 | 2026-04-15 | TBC | TBC
19 | CLAIMS | CLAIMS | Vincent Lee | Neil Li | Anurag/ Gail Gu |  | Target 10 Nov |  |  |  |  | 2026-01-15 | 2026-01-15 |  | 2026-02-15 | 2026-02-15 | 2026-03-15 | 2026-03-15 | 2026-04-15
20 | GI partnership |  | Eric Wong |  | Chee Kin Poon |  | Target 10 Nov
21 | ATAS |  |  | Jace | Raina | [6 empty] | 2026-01-15: 2025-11-17; 2026-03-15: 2025-12-12; 2026-07-20: 2026-03-10
22
23
24
25
26
27
28
29
30
is that

## (old)HK Project List - 27 Nov
| Updated as at: 27 Nov |  |  |  |  | Intake Management | [5 empty] | Platform Expected Timeline | [7 empty] | Target Lauch
# | Project | Project | HK IT Lead | CD IT Lead | Program Lead/ PM | Request Submission to ETS | ARB Review | IRM Review | ETS Review | Change Management | AliCloud DEV Approved | DEV | ETS Target Delivery (Provided by ETS) DEV | SIT | ETS Target Delivery (Provided by ETS) SIT | UAT | ETS Target Delivery (Provided by ETS) UAT | Pre-PROD/PROD/DR | ETS Target Delivery (Provided by ETS) PRD | Tech Launch | Business Go-Live | Update | Risk | Remarks | AI Model | PII Data/PRD Data | UAT Readines for PRD Gol ive
1 | Quantum - JARVIS | Quantum - JARVIS | Jerry | Darren Du | Janelle/ Cynthia | Completed | Completed | Completed | Completed | Completed | Completed | 2025-07-15 | 2025-07-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-09-26 | 2025-09-26 | 2025-10-18 | 2025-11-02 | 13-Nov: Louis to send us CI to check if included for AliCloud
2 | Distribution Compensation System (DCS) revamp | Distribution Compensation System (DCS) revamp | Theresa | Lamar Wei | Janelle/ Kelvin | Completed | Completed | Completed | Completed | Completed | Completed | 2025-07-15 | 2025-07-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-08-15 | 2025-12-06 | 2025-09-26 | 2025-12-28 | 2026-01-04 | 27-Nov: Request PRD vendor access on monitoring and logging (Aubrey to review) DB encryption can be enable by apps team(WIP) PostgreSQL - pgcrypto — cryptographic functions 25Nov: Vendor puts KMS on dev and testing. PRD support on db access - ODS (Lamer to discuss with Jeff) 20Nov: DR test review meeting(Sunny) 18-Nov: project schedule posptoned to 4-Jan. 28-Dec is the tech luanch. DR at 20-Dec(19-Dec signoff by business owner). SIT testing is in progress and UAT test will be started at 2-Dec. KMS issue is resolved(no major issue) SSL is still not resolved 13-Nov: Provided solution to vendor and how it will be hanlded with KMS(WIP)(Lamer)(ETA: TBC) 11-Nov: Under SIT and working on fixing issue(Theresa) Length of KMS and working with vendor on docker file to fix the issue(Lamar) DR for DCS might need downtime from Jarvis(Theresa) | SSL connection will need to enable(still testing) | move PRD From 12/13/2025 to 01/04/2026 Tech launch from 6-Dec to 28-Dec |  | Yes | 1) Not signed UAT 2) Not fully THR\CSPM(depends on 1)
3 | IDP Solution | IDP Solution | Jason Chan (Innovation) | Jakey Wu | Barry Cheung | Completed | 2025-09-15 | Completed | Completed | Completed | Completed | 2025-09-15 | 2025-09-29 | 2025-09-30 | 2025-10-24 | 2025-10-15 | 2025-11-18 | 2025-10-15 | 2025-11-18 | 2026-01-15 | 2026-01-22 | 27-Nov: KMS working in UAT Rocket MQ is unstable(50% failure and 50% success)(Followup with Jakey\Jeff\Darren) AI approval(No update) AI protection(There is a test ) 25-Nov: KMS on UAT is working Rocket MQ is still not connected(WIP)(Alan can help to troubleshoot) LLM is still under approval(Jonah) 21-Nov: No update on Jonah and Edward on the status update on AI approval as it will affect UAT testing(Jason\Yeap) - No ADB is using on IDP(Jason to confirm with Jonah\AA)*ADB has embeedded AI - UAT testing KMS and Rocket MQ testing in progress e.g. firewall(Rabbit changes to Rocket) - For hardening, it will be CSPM 18-Nov: Under UAT testing. KMS firewall is still WIP(Jeff and Jason to work together) . Rabbit MQ access issue(Alibaba team to help for alternative way), New AI approval(Working with AA in this afternoon). Core service needs DR(ACK has active-active design in AliCloud - Jason prepares a DR test plan) 13-Nov qwen3-vl-plus, qwen-vl-max, qwen-vl-max-0813, qwen3-vl-plus-2025-09-23 required in AliCloud(Jakey and Jason confirms required)(These AI is not approved - Jason is working on approval with Roy/Jonah) to verify UAT env tomorrow and firewall is pending to open(Jakey) | - New AI not approved to use - qwen3-vl-plus, qwen-vl-max, qwen-vl-max-0813, qwen3-vl-plus-2025-09-23(AA and ADO team is working on approval) - AI protection |  | Yes | Yes | 1) Not signed UAT 2) Not fully THR\CSPM(depends on 1) 3) AI not approved
4 | NBUW/FUW (Future Underwriting Blueprint) ¦ GenAI Powered-up Underwriting (For AA Team) | NBUW/FUW (Future Underwriting Blueprint) ¦ GenAI Powered-up Underwriting (For AA Team) | Charles Ngo | Jeremy Wu/Bill Fu | Edward/ Edward | Completed | 2025-10-13 |  |  |  |  | 2025-10-13 | 2025-11-07 | 2025-10-31 | 2025-11-07 | 2025-10-31 | 2025-11-22 | 2025-11-30 | 12/15/2025(need change) | N/A | 2026-01-25 | 27-Nov: Approved Embedded is enable 25-Nov: ADB approval is required on ADB-AI embedded(Every Monday on ARB meeting)(Harry\Jamie) 20-Nov: Jonah confirmed ADB-AI embedded is not on playbook and yet to confirm(Jonah\Charles) 18-Nov: Qwen 2.0 setup at UAT. ADB-AI model requests approval 13-Nov: qwen3-vl-plus, qwen-vl-max, qwen-vl-max-0813, qwen3-vl-plus-2025-09-23 are not required(Charles) Qwen3.0 is required only(Charles) ADB - AI search is required(Charles)(Jeremey is contact point of AA team)(To discuss with Sunny) 11-Nov: UAT: ADB & ADBAI part, we don't have security approval for it. Need Yunnie Yin approval for this into UAT & PRD *Cloud Flow will be ready at AliCloud-HK at 20-Nov | ADB with embedded and revamped Qwen-3 and medical(DEV\SIT , apps can enable AI embedded) | New AI not approved to use - qwen3-vl-plus, qwen-vl-max, qwen-vl-max-0813, qwen3-vl-plus-2025-09-23(Apps team is working on approval) ] - not required | Yes | Yes | 1) Not signed UAT 2) Not fully THR\CSPM(depends on 1) 3) AI not approved
5 | NBUW/FUW (Future Underwriting Blueprint) ¦ One Single View NBUW Platform | NBUW/FUW (Future Underwriting Blueprint) ¦ One Single View NBUW Platform | Charles Ngo | Jenny He / Aden | Edward/ Cayden | 2025-07-30 | 01-Sep-25 (SDR2) | Completed | Completed | Completed | Completed | 2025-09-15 | 2025-10-21 | 2025-10-31 | 2025-10-30 | 2025-10-31 | 2025-11-10 | 2025-11-30 | 2025-12-15 | 2025-11-02 | 2026-01-03 | 27-Nov: CloudFlow is enable(WIP) 25-Nov: CloudFlow did the hardening and waiting for IRA to confirm to release 20-Nov: Cloud flow is setup at HK and setup at DEV waiting IRA to review 18-Nov: Waiting for Cloud flow(To confirm Dongmei approval first before 20-Nov) 13-Nov: Cloud flow should be ready at 20-Nov and ETS ready at 26-Nov Tech launch at 2-Nov without cloudflow at PRD now(no AliCloud) 6 Nov: Exception will be secured for 3 Jan '26 Go-Live. Sep: engaged ETS and Ali in Q2 (before excel kicks-in); excel request submit date: 30-Jul-26. | Cloudflow is not ready at AliCloud HK until 20-Nov Go Live date at 3-Jan(change freeze) | 10 Nov: CloudFlow SG 20 Nov: CloudFlow HK will be available & target service enable in FUW UAT on 27 Nov. |  | Yes | 1) Not signed UAT 2) Not fully THR\CSPM(depends on 1)
6 | FUW (Future Underwriting Blueprint) ¦ Digital Submission Enhancement (ePOS) | FUW (Future Underwriting Blueprint) ¦ Digital Submission Enhancement (ePOS) | Frederick Tsui | Jenny He | Edward/ Flora | 2025-09-17 | 01-Sep-25 (SDR1) |  |  |  |  | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-02-01 | 2026-02-15 | 2026-02-15 | 2026-03-15 | 2026-03-15 | 2026-04-01 | 2026-04-01 | Should not be started depends on 4) and 5)
7 | Replatform Marketing Campaign System (Leads Generation) | Replatform Marketing Campaign System (Leads Generation) | Albert/Tristra | Cade Deng | Janelle/ Bowie Lee | 2025-09-17 | 2025-07-21 |  |  |  |  | 2025-10-13 | 2025-10-21 | 2025-10-21 | 2025-10-21 | 2025-11-20 | 2025-11-20 | 2025-12-15 | 2025-12-15 | 2025-12-19 | 2026-01-03 | 27-Nov: Fixed timeout issue Firewall will enable today for ingress(will plan for UAT test tomorrow) PRD firewall is plan to submit earlier(UAT signoff date is planned 25-Dec) 25-Nov: Configure KMS in UAT and SIT but having timeout issue(Cade to work with Jeff team)(UAT signoff is on 20-Nov: Firewall submitted on UAT on Thursday. AAD is progress 18-Nov: <Not joined> 13-Nov: DEV is just deployed and will start test. UAT pending firewall(Cade) 3-Jan is change freeze and no change of go live date(Cade) to work through solution with Sunny(Cade) 11-Nov: Under DEV and SIT testing(Trista) To know the IPs of PRD before 7-Dec(for firewall) | Go Live date at 3-Jan(change freeze) |  |  | Yes | 1) Not signed UAT 2) Not fully THR\CSPM(depends on 1)
8 | Agency Room Booking System | Agency Room Booking System | Tony Lin/Richard/Albert | Michael Mei | Carol Teoh | 2025-09-17 | 2025-09-29 | WIP |  |  |  | 2025-10-13 | 2025-10-21 | 2025-10-27 | 2025-10-21 | 2025-10-27 | 2025-11-07 | 2025-11-30 | 2025-11-30 | N/A | 2026-01-04 | 27-Nov: Pen test 1-Dec and 19-Dec UAT is still in progress 25-Nov: UAT env need permission to setup token(Aubrey) Firewall will need to open for authenication(Yoyo) 20-Nov: UAT is setting up with ADO and target testing in next week. Penetration test is arranged in next week. scanning of source code is required to vendor(TBC) 18-Nov: Penetration test is not confirmed. DEV is in progress and no issue. UAT will start next week 13-Nov: Start testing on DEV. Next week will have new release from vendor(Tony) 4-Jan is still the go live date(Tony) 11-Nov: Not started yet on DEV | Go Live date at 3-Jan(change freeze) |  |  | Yes | 1) Not signed UAT 2) Not fully THR\CSPM(depends on 1)
9 | Data Quality and Governance Transformation (ODS) | Data Quality and Governance Transformation (ODS) | Terence Leung Micheal Cheng | Sourav/Ranjith | Yeap/ Gary | 2025-09-17 | 2025-09-29 |  |  |  |  | 2025-10-13 | 2025-10-21 | 2025-10-13 | 2025-10-21 | 2025-10-31 | 2025-11-07 | 2025-11-11 | 2025-11-17 | N/A | 2026-01-10 | 27-Nov: Flink is enabled and working on testing(Internal DNS resolution for Flink only) 25-Nov: Flink will need to open and under IRA review(Edison) 20-Nov: On track and go to SIT after DEV 18-Nov: <Sourav><Ranjith> testing in dev(ETA:25-Nov). to add Flink and datawork on DEV Jeff comments in purple Potential Risk for Dataworks to go live (THR) - New Product Flink required 13-Nov: Under Dev testing (Sourav) Add Flink is approved by HK ARB(Harry to provide pattern to use)(To confirm setup time after Harry) Some is on UAT already - Data work is also required(Jeff) | Flink(new service) |  |  | Yes | 1) Not signed UAT 2) Not fully THR\CSPM(depends on 1)
10 | CAS modernization | CAS modernization | Wilson/Ka Fai | Sammi Wan | Yeap/ Gary | 2025-09-17 | 29-Sep-25 (SDR 3) |  |  |  |  | 2025-10-25 | 2025-10-24 | 2025-11-25 | 2025-10-28 | 2025-11-25 | 2025-11-28 | 2026-01-02 | 2026-01-02 | N/A | 2025-11-30
11 | DCS: Phase 2 | DCS: Phase 3 | Theresa Cheung | Lamar Wei | Janell/ Kelvin Mak | 2025-09-17 | 2025-09-01 |  |  |  |  | 2025-10-20 | 2025-10-29 | 2025-12-15 | 2025-12-15 | 2026-01-15 | 2026-01-15 | 2026-02-15 | 2026-02-15 | 2026-03-15 | 2026-07-20
12 | ATAS |  |  | Jace | Raina | [6 empty] | 2026-01-15: 2025-11-17; 2026-03-15: 2025-12-12; 2026-07-20: 2026-03-10 | UAT testing now(ETA:3-Dec to completed UAT testing) | Max Compute and Data Work
13 | MCF | MCF | Pong Soon Lung | Ronaldo Wang | [7 empty] | 2026-03-31 | 2025-12-15 | 2026-03-31 | 2026-01-15 | 2026-04-30 | 2026-02-15 | 2026-05-31 | 2026-03-15 | 2026-06-15 | 2026-07-01
14 | CTOM | CTOM | Vincent Lee | Neil Li | Anurag/ Gail |  | 29-Sep-25 (SDR 1) |  |  |  |  | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-02-15 | 2026-02-15 | 2026-03-15 | 2026-03-15 | 2026-04-15 |  | 2026-06-01
15 | Agency printing | Agency printing | Joseph Wong | Serena Wang | TBC | [6 empty] | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-02-15 | 2026-02-01 | 2026-03-15 | 2026-03-01 | 2026-04-15 | 2026-03-26 | 2026-06-01
16 | GLH (Orion) | GLH (Orion) | Judith / Eric Wong |  | Anurag/ TBC | [6 empty] | 2026-01-15 | 2026-01-15 |  | 2026-02-15 | 2026-02-15 | 2026-03-15 | 2026-03-15 | 2026-04-15 |  | 2026-06-01
17 | MOVE 2.0 | MOVE 2.1 | Albert |  | Emily/ Kenneth Li |  | Target 10 Nov |  |  |  |  | 2026-01-05 | 2026-01-05 |  | 2026-02-15 | Q1-26 | 2026-03-15 | 2027-01-03 | 2026-04-15 | TBC | TBC
18 | Sky | Sky | Albert |  | James Cheung |  | James |  |  |  |  | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-02-15 | 2026-04-01 | 2026-03-15 | 2027-01-03 | 2026-04-15 | 2027-01-15 | 2027-01-30
19 | Quantum LeadGen by MarTech CP 2 | Quantum LeadGen by MarTech CP 3 | Albert Ahg |  | Janelle/ Bowie Lee |  | Target 10 Nov |  |  |  |  | 2026-01-05 | 2026-01-05 |  | 2026-02-15 | Q1-26 | 2026-03-15 | 2026-07-19 | 2026-04-15 | TBC | TBC
20 | CLAIMS | CLAIMS | Vincent Lee | Neil Li | Anurag/ Gail Gu |  | Target 10 Nov |  |  |  |  | 2026-01-15 | 2026-01-15 |  | 2026-02-15 | 2026-02-15 | 2026-03-15 | 2026-03-15 | 2026-04-15
21 | GI partnership |  | Eric Wong |  | Chee Kin Poon |  | 2025-11-24 |  |  |  |  | 2026-01-15: 2026-01-05; 2026-01-15: 2026-01-05; 2026-02-15: 2026-02-01; 2026-03-15: 2026-03-15 | 2026-07-20 | 2026-07-20
22 | IUL |  | George Lau |  | Jess Wong | 2025-11-27 | 2025-11-24 |  |  |  |  | 2026-01-15: 2025-12-15; 2026-01-15: 2025-12-15; 2026-02-15: 2026-01-09; 2026-03-15: 2026-02-02 | 2026-05-04 | 2026-05-17
| Additional item |  | Requirement |  | Owner
| Global year-end Change Freeze Cycle will start Wednesday December 24th, 2025, at 12:00pm (noon) EST/HKT until Thursday January 8th, 2026, at 11:59am EST/HKT. |  | If go live between change freeze. 1) HK team will need to raise and get ECR approved for any change required(ETS will not raise any ECR), 2) Any change required on 3-Jan will need well plan as Azure change might not have global team to perform the work |  | HK Apps Owner
| New AI Service |  | Apps owner will need to get approval on AI at AliCloud i)Use case or Prompt Enginnering(ADO & AA) ii) Foundation LLM Evaluation(Eugene Wen, Global Data Technology ) |  | Apps Owner, ADO, AA, GD
| New Service(Non AI) |  | ETS-IRA and BU-IRA will need to approve before enable at AliCloud(Same as Azure) |  | ETS-IRA and BU-IRA
| Other projects timeline |  | To provide\revise the timeline |  | Yeap
| No ECS (VM) should be created |  | VM creation requires approval |  | Harry

## (old)HK Project List-22Sep
[5 empty] | Intake Management | [5 empty] | Platform Expected Timeline | [5 empty] | Target Lauch
# | Project | Scope | IT lead | Program Lead/PM | Request Submission | ARB Review | IRM Review | ETS Review | Change Management | AliCloud DEV Approved | DEV | ETS Target Delivery | SIT/UAT | ETS Target Delivery | Pre-PROD/PROD/DR | ETS Target Delivery | Tech | Business Go-Live | Requirement on Ali | Remarks
1 | Quantum - JARVIS | Chatbot for Agent on Agent platform | Jerry |  | Completed | [5 empty] | 2025-07-15 | 2025-07-15 | 2025-08-15 | 2025-08-15 | 2025-09-26 | 2025-09-26 | 2025-10-18 | 2025-11-01 | 1. Alibaba LLM model, RAG and Vector DB related GenAI service 2. AliCloud sandbox env & testing account 3. Network Firewall, CDN 4. Chatbot front-end setup with React (ACK, API Gateway) 5. ACK foundation 6. PostgreSQL 7. Connection to ADF, Databricks, Data lake, ODS 8. Message queue 9. ADX logging 10. New relic monitoring 11. Connection to Gamma, AKS
2 | Distribution Compensation System revamp | C2L components setup on Ali for some bonus type | Theresa |  | Completed | [5 empty] | 2025-07-15 | 2025-07-15 | 2025-08-15 | 2025-08-15 | 2025-09-26 | 2025-09-26 | 2025-11-29 | 2025-12-13 | 1. Internal Access to website 2. PostgreSQL 3. ACK 4. Object Storage to store files (ie. OSS) 5. Redis 6. Password Vault to store the DB password 7. Internal SSO with Active Directory MFCGD domain, with MFA enabled 8. CICD - vendor provide the container image (OS: RHEL/Ubuntu; AppServer: Jboss EAP) from their Nexu repository (outside Manulife), they are using VDI machine to access Manulife network. They perform development in their own development env, not Manulife. - deploy to PROD, auto deploy to DR, no manualAPIM - Connect IBM Aspera and Artifactory 11. Integration with ADX, can limit vendor to read logs for vendor software only (or Ali Alternatives) 12. Integration with New Relic (or Ali Alternatives) 13. CA workload can run DCS batch by calling DCS API, need AAD? 14. Public Access to website (2026) - Distribution Portal - another website in alicloud connect Manulife Connect Framework (MCF - SG) - ADO (Azure AKS) to Distribution portal at Alicloud 15. Connection to ADF, ADF will sync data from/to Manulife oracle DB, AKS Azure DB to PostgreSQL 16. Non-prod (Dev, SIT, UAT) and Prod are separate | Some fundamental functions are also required. eg. network policy, DR location, cyberark to get secret to login prod DB/Portal, etc 14.1: MCF - SG (https://api.emmprd.asia.manulife.com/ext/nest-connect-gatewayd/interaction/3S5zu-ALp6ylbTmhYvAtS&lang=zh-hant) 14.2: ADO (Azure AKS) ( https://api.hkprod.manulife.com.hk/ext/hk-ado-portal-web-app/login/agent)
3 | IDP Solution | Shared Component for HKIT | Jason Chan (Innovation) |  |  | 2025-09-15 |  |  |  |  | 2025-09-15 | 2025-09-30 | 2025-09-30 | 2025-10-24 | 2025-10-15 | 2025-11-18 | 2025-11-16 | ######## | Ali Model Studio AsparaDB ACK Functions Compute OSS EventBridge API Gateway PAI for classification of image Qwen suite of models (Qwen-vl-max, Qwen-vl-ocr) AI Doc Doc Parser | 2 items not part of JARVIS: DocParser, PAI 15-Sep ARB: SDR1 approved
4 | FUW (Future Underwriting Blueprint) ¦ GenAI Powered-up Underwriting (For AA Team) | AI Compoents for AA team | Charles Ngo | Edward/Edward |  | Target: 13 Oct |  |  |  |  | 2025-09-15 | 2025-10-21 | 2025-10-31 | 2025-11-21 | 2025-11-30 | 2025-12-26 |  | Jan-26 | Similar to Jarvis '- Ali Model studio '- Ali PAI '- Ali AI Guardrail '- Alibaba Qwen LLM model, RAG and Vector DB, AI Doc - ACK Python for AA team - CI/CD pipeline - Redis/PostgreSQL - OSS | Dev: workaround feasible, but need to confirm with Jonah
5 | FUW (Future Underwriting Blueprint) ¦ One Single View NBUW Platform (NBUWS) | STP without human touch migrate all NB related services to ali | Charles Ngo | Edward/Cayden | engaged ETS and Ali in Q2 (before excel kicks-in); excel request submit date: 30-Jul-25 | 25-May-25 (SDR1) 01-Sep-25 (SDR2) |  |  |  |  | 2025-09-15 | 2025-10-21 | 2025-10-31 |  | 2025-11-30 |  | 2025-11-02 | 2026-01-03 | 1. Ali Landing zone: - Account and resource architecture - RAM Account/Subscription and hierarchy. - Account policy and role/permissions. - Resource deployment approach and management policy. - Tags - Networking planning and VPC, NSG, Route table creation - External network connection - RAM account design and RBAC - Firewall and DDos , key management - Compliance baseline - Monitoring/Alert and log trace system - CI/CD pipeline(this one can reach out Raymond Li first ). - DR solution, include container, cluster, DB. 2. ACK setup and governance: - ACK networking setup(istio, lb) - ACK cluster setup include dev/sit/uat/prod - Service access with and authenticate(Istio/RRSA) - Image Repository(ACR) 3. Ali PaaS Product: - Event Bridge - RDS(Sql Server) - RabbitMQ/RocketMQ(base on use case) - OSS | Dev not ready: if UAT env in Nov is not valid, no ground to use SG Dev. Option 1 ¦ begins Dev in Jan 2026 - NO, huge schedule impact Option 2 ¦ pivot to Azure+AWD - given Azure has no Cloudflow
6 | FUW (Future Underwriting Blueprint) ¦ Digital Submission Enhancement (ePOS) | - ePOS (AKS hosted) call IDP, NBUWS & GenAI Ali services. AKS to call ACK-IDP/FUW - firewall request | Frederick | Edward/Flora |  | 01-Sep-25 (SDR1) |  |  |  |  | 2025-10-25 |  | 2025-10-25 |  | 2025-04-25 |  | N/A | 2025-04-25 | - Require for ePOS under Azure to One Platform Ali Cloud - Require for ePOS to call IDP under Ali Cloud - Requrie for ePOS to call Gent AI under Ali Cloud - Dependency with item 4, 5, 6 for Future Underwriting Blueprint
7 | Replatform Campaign System (Leads Generation) | New campaign system. | Albert | Bowie Lee |  | Approved on July 21 2025 |  |  |  |  | 2025-07-15: 2025-09-25; 2025-08-15: 2025-11-25; 2025-11-29: 2026-01-01; 2025-12-13: Jan-26 | - Polar DB (PolarDB for PostgreSQL) - Campaign backend setup with Springboot - Campaign frontend setup with Angluar / React - Azure AD authentication - Redis - Message queue - Object Storage Service - Data Lake / ADF / Databrick injection with Azure Cloud - Outbound call to external API
8 | CAS modernization | DB migration from Oracle to PolarDB CSMS frontend migrate to ACK | Wilson/Ka Fai | Yeap/Gary |  | Target: 29 Sep |  |  |  |  | 2025-10-25 | 2025-10-24 | 2025-11-25 | 2025-11-28 | Jan/Feb-26 |  | 2025-05-01 | Sep-26 | - Polar DB (PolarDB for PostgreSQL(Compatible with Oracle)) - CSMS backend setup with Springboot - CSMS frontend setup with Springboot - Azure AD authentication - Redis - Message queue - Object Storage Service - Data Lake / ADF / Databrick injection with Azure Cloud - Outbound call to external API
9 | Agency Room Booking System |  | Tony Lin / Albert | [7 empty] | 2025-12-13: 2025-01-26 | ACK
10 | MOVE 2.0 | MOVE 2.0 backend hosted in Ali | Albert |  |  | Target 10th Nov |  |  |  |  | 2025-10-25 |  | Q1-26 |  | 2025-10-26 |  | TBC | TBC | - ApsaraDB for MongoDB - MOVE backend setup with Springboot / NodeJS - MOVE internal frontend setup with Angluar / React - Public API endpoint for external system callback - Redis - Object Storage Service - Outbound call to external API
11 | MCF | MCF Gateway and MCF backend | Pong Soon Lung | [7 empty] | 2025-07-15: 2025-10-25; 2025-11-29: TBC; 2025-12-13: TBC | ApsaraDB for MongoDB Redis Keyvault RMQ Public API endpoint API Gateway Outbound SMTP call
12 | Agency printing |  | Joseph Wong | [7 empty] | 2025-07-15: 2025-11-25; 2025-08-15: 2025-12-25; 2025-09-26: 2025-01-26; 2025-12-13: 2025-03-26
13 | CTOM |  | Vincent Lee |  |  | Target 10th Nov |  |  |  |  | 2025-07-15: 2025-01-26; 2025-12-13: 2025-06-26
14 | GLH (Orion) |  | Judith / Eric Wong | [7 empty] | 2025-07-15: 2025-01-26; 2025-12-13: 2025-06-26 | First Drop: Jun 26 (Subject to revise based on vendor finalization)

## CHG
Item | Details | DEV\SIT\UAT | PRD | Remarks
New Service | Not on THR or AI | After reviewed with IRA, it could be tested | Cannot be used without AI approval and IRA Approval
New account(add\change\delete) | Approved by ETS-IRA(Aubrey) | Enforced | Enforced
Application Go Live | Apps IRA Approved(Sunny) *Includes Penetration test, DAST and etc |  | CHG approved with IRA approved evidence | Follow same Manulife standards

## HK Project List - 24 Sep (hidden)
| Updated as at: 24 Sep |  |  |  | Intake Management | [5 empty] | Platform Expected Timeline | [5 empty] | Target Lauch
# | Project | Scope | HK IT Lead | Program Lead/ PM | Request Submission | ARB Review | IRM Review | ETS Review | Change Management | AliCloud DEV Approved | DEV | ETS Target Delivery | SIT/UAT | ETS Target Delivery | Pre-PROD/PROD/DR | ETS Target Delivery | Tech | Business Go-Live | Requirement on Ali | Remarks
1 | Quantum - JARVIS | Chatbot for Agent on Agent platform | Jerry |  | Completed | [5 empty] | 2025-07-15 | 2025-07-15 | 2025-08-15 | 2025-08-15 | 2025-09-26 | 2025-09-26 | 2025-10-18 | 2025-11-01 | 1. Alibaba LLM model, RAG and Vector DB related GenAI service 2. AliCloud sandbox env & testing account 3. Network Firewall, CDN 4. Chatbot front-end setup with React (ACK, API Gateway) 5. ACK foundation 6. PostgreSQL 7. Connection to ADF, Databricks, Data lake, ODS 8. Message queue 9. ADX logging 10. New relic monitoring 11. Connection to Gamma, AKS
2 | Distribution Compensation System (DCS) revamp | C2L components setup on Ali for some bonus type | Theresa |  | Completed | [5 empty] | 2025-07-15 | 2025-07-15 | 2025-08-15 | 2025-08-15 | 2025-09-26 | 2025-09-26 | 2025-11-29 | 2025-12-13 | 1. Internal Access to website 2. PostgreSQL 3. ACK 4. Object Storage to store files (ie. OSS) 5. Redis 6. Password Vault to store the DB password 7. Internal SSO with Active Directory MFCGD domain, with MFA enabled 8. CICD - vendor provide the container image (OS: RHEL/Ubuntu; AppServer: Jboss EAP) from their Nexu repository (outside Manulife), they are using VDI machine to access Manulife network. They perform development in their own development env, not Manulife. - deploy to PROD, auto deploy to DR, no manualAPIM - Connect IBM Aspera and Artifactory 11. Integration with ADX, can limit vendor to read logs for vendor software only (or Ali Alternatives) 12. Integration with New Relic (or Ali Alternatives) 13. CA workload can run DCS batch by calling DCS API, need AAD? 14. Public Access to website (2026) - Distribution Portal - another website in alicloud connect Manulife Connect Framework (MCF - SG) - ADO (Azure AKS) to Distribution portal at Alicloud 15. Connection to ADF, ADF will sync data from/to Manulife oracle DB, AKS Azure DB to PostgreSQL 16. Non-prod (Dev, SIT, UAT) and Prod are separate | Some fundamental functions are also required. eg. network policy, DR location, cyberark to get secret to login prod DB/Portal, etc 14.1: MCF - SG (https://api.emmprd.asia.manulife.com/ext/nest-connect-gatewayd/interaction/3S5zu-ALp6ylbTmhYvAtS&lang=zh-hant) 14.2: ADO (Azure AKS) ( https://api.hkprod.manulife.com.hk/ext/hk-ado-portal-web-app/login/agent)
3 | IDP Solution | Shared Component for HKIT | Jason Chan (Innovation) | Alice Zhao |  | 2025-09-15 |  |  |  |  | 2025-09-15 | 2025-09-30 | 2025-09-30 | 2025-10-24 | 2025-10-15 | 2025-11-18 | 2025-11-16 | 2025-11-30 | Ali Model Studio AsparaDB ACK Functions Compute OSS EventBridge API Gateway PAI for classification of image Qwen suite of models (Qwen-vl-max, Qwen-vl-ocr) AI Doc Doc Parser | 2 items not part of JARVIS: DocParser, PAI 15-Sep ARB: SDR1 approved
4 | NBUW/FUW (Future Underwriting Blueprint) ¦ GenAI Powered-up Underwriting (For AA Team) | AI Compoents for AA team Similar as Jarvis - utilizing existing resources | Charles Ngo | Edward/ Edward |  | Target: 13 Oct |  |  |  |  | 2025-09-15 | Same as Jarvis | 2025-10-31 | Same as Jarvis | 2025-11-30 | Same as Jarvis |  | Jan-26 | Similar to Jarvis '- Ali Model studio '- Ali PAI '- Ali AI Guardrail '- Alibaba Qwen LLM model, RAG and Vector DB, AI Doc - ACK Python for AA team - CI/CD pipeline - Redis/PostgreSQL - OSS | Dev: workaround feasible, but need to confirm with Jonah
5 | NBUW/FUW (Future Underwriting Blueprint) ¦ One Single View NBUW Platform | STP without human touch migrate all NB related services to Ali | Charles Ngo | Edward/ Cayden | engaged ETS and Ali in Q2 (before excel kicks-in); excel request submit date: 30-Jul-25 | 25-May-25 (SDR1) 01-Sep-25 (SDR2) |  |  |  |  | 2025-09-15 | 2025-10-21 | 2025-10-31 | SIT: 30-Oct-25 UAT: 10-Nov-25 | 2025-11-30 | 2025-12-15 | 2025-11-02 | 2026-01-03 | 1. Ali Landing zone: - Account and resource architecture - RAM Account/Subscription and hierarchy. - Account policy and role/permissions. - Resource deployment approach and management policy. - Tags - Networking planning and VPC, NSG, Route table creation - External network connection - RAM account design and RBAC - Firewall and DDos , key management - Compliance baseline - Monitoring/Alert and log trace system - CI/CD pipeline(this one can reach out Raymond Li first ). - DR solution, include container, cluster, DB. 2. ACK setup and governance: - ACK networking setup(istio, lb) - ACK cluster setup include dev/sit/uat/prod - Service access with and authenticate(Istio/RRSA) - Image Repository(ACR) 3. Ali PaaS Product: - Event Bridge - RDS(Sql Server) - RabbitMQ/RocketMQ(base on use case) - OSS | Dev not ready: if UAT env in Nov is not valid, no ground to use SG Dev. Option 1 ¦ begins Dev in Jan 2026 - NO, huge schedule impact Option 2 ¦ pivot to Azure+AWD - given Azure has no Cloudflow
6 | Replatform Campaign System (Leads Generation) | New campaign system. | Albert | Bowie Lee |  | Approved on July 21 2025 |  |  |  |  | 2025-07-15: 2025-09-25; 2025-08-15: 2025-11-25; 2025-11-29: 2026-01-01; 2025-12-13: Jan-26 | - Polar DB (PolarDB for PostgreSQL) - Campaign backend setup with Springboot - Campaign frontend setup with Angluar / React - Azure AD authentication - Redis - Message queue - Object Storage Service - Data Lake / ADF / Databrick injection with Azure Cloud - Outbound call to external API
7 | CAS modernization | DB migration from Oracle to PolarDB CSMS frontend migrate to ACK | Wilson/Ka Fai | Yeap/ Gary |  | Target: 29 Sep |  |  |  |  | 2025-10-25 | 2025-10-24 | 2025-11-25 | 2025-11-28 | Jan/Feb-26 |  | 2025-05-01 | Sep-26 | - Polar DB (PolarDB for PostgreSQL(Compatible with Oracle)) - CSMS backend setup with Springboot - CSMS frontend setup with Springboot - Azure AD authentication - Redis - Message queue - Object Storage Service - Data Lake / ADF / Databrick injection with Azure Cloud - Outbound call to external API
8 | DCS: Phase 2 | DCS Revamp | Theresa Cheung | Kelvin Mak | 2025-09-17 | 2025-09-30 | TBC | TBC |  |  | 2025-10-25 |  | 2025-12-01 |  | 2026-04-01 |  | 2026-07-01 | 2026-07-20
9 | Agency Room Booking System | Vendor solution (Deploy in our AKS/ACK) | Tony Lin/Richard/Albert | Carol Teoh |  | Target: 29 Sep | WIP |  |  |  | 2025-09-29 |  | 2025-10-27 |  | 2025-11-30 |  | N/A | 2025-01-04 | K8S, PSQL, Redis, CDN(Akamai) Internet facing | Pending decision if Alibaba timeline feasible
10 | MOVE 2.0 | MOVE 2.0 backend hosted in Ali | Albert |  |  | Target 10th Nov |  |  |  |  | 2025-10-25 |  | Q1-26 |  | 2025-10-26 |  | TBC | TBC | - ApsaraDB for MongoDB - MOVE backend setup with Springboot / NodeJS - MOVE internal frontend setup with Angluar / React - Public API endpoint for external system callback - Redis - Object Storage Service - Outbound call to external API
11 | MCF | MCF Gateway and MCF backend | Pong Soon Lung | [7 empty] | 2025-07-15: 2025-10-25; 2025-11-29: TBC; 2025-12-13: TBC | ApsaraDB for MongoDB Redis Keyvault RMQ Public API endpoint API Gateway Outbound SMTP call
12 | Agency printing |  | Joseph Wong | [7 empty] | 2025-07-15: 2025-11-25; 2025-08-15: 2025-12-25; 2025-09-26: 2025-01-26; 2025-12-13: 2025-03-26
13 | CTOM |  | Vincent Lee |  |  | Target 10th Nov |  |  |  |  | 2025-07-15: 2025-01-26; 2025-12-13: 2025-06-26
14 | GLH (Orion) |  | Judith / Eric Wong | [7 empty] | 2025-07-15: 2025-01-26; 2025-12-13: 2025-06-26 | First Drop: Jun 26 (Subject to revise based on vendor finalization)

## Change Request - In Queue (hidden)
No | Date | Item | Details | Raised By | Approved By(Harry for ETS Arch Team and Benson for HK Approval)
1 | 2025-07-30 | Apps change for NBUW Platform | Event Bridge | Ka Fai / Kenneth
2 | 2025-07-30 | Apps change for NBUW Platform | Function Compute | Ka Fai / Kenneth
3 | 2025-07-30 | Apps change for NBUW Platform(Enterprise Oct-2025 ready at Ali-HK) | CloudFlow | Ka Fai / Kenneth | SG only (HK starts testing at end of Aug - Jeff\Derek)
4 | 2025-07-31 | New App - NBUW target go live (Prod) in Nov 2025 | New App | Kenneth
5 | 2025-07-31 | New App - Agency Printing (Dev Nov 25, Prod Mar 26) | New App | Kenneth
6 | 2025-08-12 | New App - ODS | New App | Michael Cheng
7 | 2025-08-19 | IDP | New App | Joe Kung
8 | 2025-09-05 | create workspace following resource name "mfc modelstudio-dev-uw", enable model “qwen-max” and “qwen-plus” and “qwen-vl-max“, grant access to RAM role and workspace | Ali Model Studio | Charles Ngo
9 | 2025-10-30 | Provision RabbitMQ for IDP env | RabbitMQ | Jakey Wu | ARM approved on 27 Oct 25

## User Access Request (hidden)
Submitted Date | Submitted By | Request for | Envoirnments | Rights for Ali Services | Details | Status | IRM approval | Handle By | Complete Date | Remarks | ETS comment
2025-07-21 | Kenneth Lai | IDass - Common Account | Dev, Test | ACK, PostgreSQL, MongoDB (R,W,X),Model Studio, ADB | Louis Tang | Submitted | - | Alan | 2025-07-22
2025-07-21 | Kenneth Lai | IDass - Common Account | Dev, Test | ACK, PostgreSQL, MongoDB (R,W,X),Model Studio, ADB | Jerry Chan | Submitted |  | Alan | 2025-07-22
2025-07-21 | Kenneth Lai | IDass - Common Account | Dev, Test | ACK, PostgreSQL, OSS (R,W,X) | Kelvin Chan | Submitted |  | Alan | 2025-07-22
2025-07-21 | Kenneth Lai | IDass - Common Account | Dev, Test | ACK, PostgreSQL, OSS (R,W,X) | Lamar Wei | Submitted |  | Alan | 2025-07-22
2025-07-21 | Kenneth Lai | IDass - Common Account | Dev, Test | ACK, PostgreSQL, OSS (R,W,X) | Teresa Cheung | Submitted |  | Alan | 2025-07-22
2025-07-21 | Kenneth Lai | IDass - Common Account | Dev, Test | ACK, Model Studio, MongoDB, ADB | Bill Fu | Submitted |  | Alan | 2025-07-22
2025-07-21 | Kenneth Lai | IDass - Common Account | Dev, Test | ACK, Model Studio, MongoDB, ADB | Darren Du | Submitted |  | Alan | 2025-07-22
2025-07-21 | Kenneth Lai | IDass - Common Account | Dev, Test | ACK | Richard Yu | Submitted |  | Alan | 2025-07-22
2025-07-21 | Kenneth Lai | IDass - Common Account | Dev, Test | ACK, PostgreSQL, RocketMQ | Ka Fai Lo | Submitted |  | Alan | 2025-07-22
2025-07-21 | Kenneth Lai | IDass - Common Account | Dev, Test | ACK, Model Studio, ADB | Kenneth Lai | Submitted |  | Alan | 2025-07-22
2025-07-21 | Kenneth Lai | Trigger Build / Publish / Deploy Pipeline on Jenkins | Dev, Test, Prod | Jenkins (Azure) | Louis Tang | Submitted |  | Dennis to follow |  | Dennis to chk with Jomer/ Reymond Li, if existing env account follow existing process
2025-07-21 | Kenneth Lai | Trigger Build / Publish / Deploy Pipeline on Jenkins | Dev, Test, Prod | Jenkins (Azure) | Jerry Chan | Submitted |  | Dennis to follow |  | Dennis to chk with Jomer/ Reymond Li, if existing env account follow existing process
2025-07-21 | Kenneth Lai | Trigger Build / Publish / Deploy Pipeline on Jenkins | Dev, Test, Prod | Jenkins (Azure) | Kelvin Chan | Submitted |  | Dennis to follow |  | Dennis to chk with Jomer/ Reymond Li, if existing env account follow existing process
2025-07-21 | Kenneth Lai | Trigger Build / Publish / Deploy Pipeline on Jenkins | Dev, Test, Prod | Jenkins (Azure) | Lamar Wei | Submitted |  | Dennis to follow |  | Dennis to chk with Jomer/ Reymond Li, if existing env account follow existing process
2025-07-21 | Kenneth Lai | Trigger Build / Publish / Deploy Pipeline on Jenkins | Dev, Test, Prod | Jenkins (Azure) | Teresa Cheung | Submitted |  | Dennis to follow |  | Dennis to chk with Jomer/ Reymond Li, if existing env account follow existing process
2025-07-21 | Kenneth Lai | Trigger Build / Publish / Deploy Pipeline on Jenkins | Dev, Test, Prod | Jenkins (Azure) | Bill Fu | Submitted |  | Dennis to follow |  | Dennis to chk with Jomer/ Reymond Li, if existing env account follow existing process
2025-07-21 | Kenneth Lai | Trigger Build / Publish / Deploy Pipeline on Jenkins | Dev, Test, Prod | Jenkins (Azure) | Darren Du | Submitted |  | Dennis to follow |  | Dennis to chk with Jomer/ Reymond Li, if existing env account follow existing process
2025-07-21 | Kenneth Lai | Trigger Build / Publish Pipeline on Jenkins | Dev, Test | Jenkins (Azure) | Richard Yu | Submitted |  | Dennis to follow |  | Dennis to chk with Jomer/ Reymond Li, if existing env account follow existing process
2025-07-21 | Kenneth Lai | Trigger Build / Publish Pipeline on Jenkins | Dev, Test | Jenkins (Azure) | Ka Fai Lo | Submitted |  | Dennis to follow |  | Dennis to chk with Jomer/ Reymond Li, if existing env account follow existing process
2025-07-21 | Kenneth Lai | Trigger Build / Publish Pipeline on Jenkins | Dev, Test | Jenkins (Azure) | Kenneth Lai | Submitted |  | Dennis to follow |  | Dennis to chk with Jomer/ Reymond Li, if existing env account follow existing process
2025-07-21 | Kenneth Lai | Trigger Build / Publish Pipeline on Jenkins | Dev, Test, Prod | Jenkins (Azure) | Terence Leung | Submitted |  | Dennis to follow |  | Dennis to chk with Jomer/ Reymond Li, if existing env account follow existing process
2025-07-21 | Kenneth Lai | IDass - Common Account | Dev, Test, Prod | ACK, KMS | Tiffany GUO | Submitted |  | Alan | 2025-07-22
2025-07-21 | Kenneth Lai | IDass - Common Account | Dev, Test | ACK, Model Studio, ADB, MongoDB, OSS (R,W,X), Functions Compute, Event Bridge, API Gateway, PAI, AI Doc (if available), AI Guardrails | Jason Chan | Submitted |  | Alan | 2025-07-22 | PAI, AL Doc, AI Guardrails - To be confirmed(Ken)
2025-07-21 | Kenneth Lai | IDass - Common Account | Dev, Test | PostgreSQL, MongoDB (R) | Matthew Poon | Submitted |  | Alan | 2025-07-22
2025-07-21 | Kenneth Lai | IDass - Common Account | Dev, Test | PostgreSQL, MongoDB (R) | Winky Bok | Submitted |  | Alan | 2025-07-22
2025-07-21 | Kenneth Lai | IDass - Common Account | Dev, Test | PostgreSQL, MongoDB (R) | Michelle Yau | Submitted |  | Alan | 2025-07-22
2025-07-22 |  | IDass - Common Account | Dev, Test | ACK, MongoDB | Arya Chang |  |  | Alan | 2025-07-22 | Jarvis CD IT
2025-07-23 |  | Trigger Build / Publish / Deploy Pipeline on Jenkins | Dev, Test | Jenkins (Azure) | Arya Chang |  |  | Dennis to follow |  | Jarvis CD IT, Dennis to chk with Jomer/ Reymond Li, if existing env account follow existing process
2025-07-24 |  | IDass - Common Account | Dev, Test | ACK, MongoDB | Daniel Li |  |  | Alan | 2025-07-22 | Jarvis CD IT
2025-07-25 |  | Trigger Build / Publish / Deploy Pipeline on Jenkins | Dev, Test | Jenkins (Azure) | Daniel Li |  |  | Dennis to follow |  | Jarvis CD IT, Dennis to chk with Jomer/ Reymond Li, if existing env account follow existing process
2025-07-26 |  | IDass - Common Account | Dev, Test | ACK, MongoDB | Dylan Liu |  |  | Alan | 2025-07-22 | Jarvis CD IT
2025-07-27 |  | Trigger Build / Publish / Deploy Pipeline on Jenkins | Dev, Test | Jenkins (Azure) | Dylan Liu |  |  | Dennis to follow |  | Jarvis CD IT, Dennis to chk with Jomer/ Reymond Li, if existing env account follow existing process
2025-07-28 |  | IDass - Common Account | Dev, Test | ACK, MongoDB | Aurora Yang |  |  | Alan | 2025-07-22 | Jarvis CD IT
2025-07-29 |  | Trigger Build / Publish / Deploy Pipeline on Jenkins | Dev, Test | Jenkins (Azure) | Aurora Yang |  |  | Dennis to follow |  | Jarvis CD IT, Dennis to chk with Jomer/ Reymond Li, if existing env account follow existing process
2025-07-30 |  | IDass - Common Account | Dev, Test | ACK, MongoDB | Jack Huang |  |  | Alan | 2025-07-22 | Jarvis CD IT
2025-07-31 |  | Trigger Build / Publish / Deploy Pipeline on Jenkins | Dev, Test | Jenkins (Azure) | Jack Huang |  |  | Dennis to follow |  | Jarvis CD IT, Dennis to chk with Jomer/ Reymond Li, if existing env account follow existing process
2025-07-24 | Jason Chan | IDass - Common Account | Dev, Test | ACK, Model Studio, ADB, MongoDB, OSS (R,W,X), Functions Compute, Event Bridge, API Gateway, PAI, AI Doc (if available), AI Guardrails | Joe Kung |  |  | Alan |  | PAI, AL Doc, AI Guardrails - To be confirmed(Ken)
2025-07-24 | Jason Chan | IDass - Common Account | Dev, Test | ACK, Model Studio, ADB, MongoDB, OSS (R,W,X), Functions Compute, Event Bridge, API Gateway, PAI, AI Doc (if available), AI Guardrails | Saken Gazezov |  |  | Alan |  | PAI, AL Doc, AI Guardrails - To be confirmed(Ken)
2025-07-24 | Jason Chan | IDass - Common Account | Dev, Test | ACK, Model Studio, ADB, MongoDB, OSS (R,W,X), Functions Compute, Event Bridge, API Gateway, PAI, AI Doc (if available), AI Guardrails | Castiel Tong |  |  | Alan |  | PAI, AL Doc, AI Guardrails - To be confirmed(Ken)
2025-07-29 | Jason Peng | Trigger Build / Publish / Deploy Pipeline on Jenkins | Dev, Test, Prod | Jenkins (Azure) | Jason Peng | Approved for SIT and Dev only |  | Ang |  | NB CD IT
2025-07-29 | Jason Peng | Trigger Build / Publish / Deploy Pipeline on Jenkins | Dev, Test, Prod | Jenkins (Azure) | Aden Zhang | Approved for SIT and Dev only |  | Ang |  | NB CD IT
2025-07-29 | Jason Peng | Trigger Build / Publish / Deploy Pipeline on Jenkins | Dev, Test, Prod | Jenkins (Azure) | Jack Deng | Approved for SIT and Dev only |  | Ang |  | NB CD IT
2025-07-29 | Jason Peng | Trigger Build / Publish / Deploy Pipeline on Jenkins | Dev, Test, Prod | Jenkins (Azure) | Victor Wu | Approved for SIT and Dev only |  | Ang |  | NB CD IT
2025-07-29 | Jason Peng | IDass - Common Account | Dev, Test | CloudFlow,ACK, ADB, MongoDB,PolarDB,OSS (R,W,X), Functions Compute, Event Bridge, API Gateway,VPC(R),ARMS,SLS | Jason Peng | Approved for SIT and Dev only |  | Ang |  | NB CD IT
2025-07-29 | Jason Peng | IDass - Common Account | Dev, Test | CloudFlow,ACK, ADB, MongoDB,PolarDB,OSS (R,W,X), Functions Compute, Event Bridge, API Gateway,VPC(R),ARMS,SLS | Aden Zhang | Approved for SIT and Dev only |  | Ang |  | NB CD IT
2025-07-29 | Jason Peng | IDass - Common Account | Dev, Test | CloudFlow,ACK,Functions Compute, Event Bridge | David Yang | Approved for SIT and Dev only |  | Ang |  | NB CD IT
2025-07-29 | Jason Peng | IDass - Common Account | Dev, Test | CloudFlow,ACK,Functions Compute, Event Bridge | Victor Wu | Approved for SIT and Dev only |  | Ang |  | NB CD IT
2025-07-29 | Jason Peng | IDass - Common Account | Dev, Test | CloudFlow,ACK,Functions Compute, Event Bridge | Jack Deng | Approved for SIT and Dev only |  | Ang |  | NB CD IT
2025-07-29 | Jason Peng | IDass - Common Account | Dev, Test | CloudFlow,ACK, ADB, MongoDB,PolarDB,OSS (R,W,X), Functions Compute, Event Bridge, API Gateway,VPC(R),ARMS,SLS | Charles Ngo | Approved for SIT and Dev only |  | Ang |  | NB HK IT
2025-07-29 | Scott li | IDass - Common Account | Dev, Test | ACK,ARMS,SLS | Scott li | v |  | Ang |  | ESS CD IT | CloudFlow, Funtions Compute, Event Bridge are not in App requirement scope, please connect with Kenneth for approval
2025-07-29 | Ian Cheng | IDass - Common Account | Dev, Test | ACK | Ian Cheng |  |  |  |  | ESS CD IT
2025-07-29 | Zero Mu | IDass - Common Account | Dev, Test, Prod | ACK, ARMS,SLS,API GateWay, CloudFlow, Funtions Compute, Event Bridge | Zero Mu | Approved for SIT and Dev only |  | Ang |  | HK DevOps | CloudFlow, Funtions Compute, Event Bridge are not in App requirement scope, please connect with Kenneth for approval
2025-07-29 | Zero Mu | IDass - Common Account | Dev, Test, Prod | ACK, ARMS,SLS,API GateWay, CloudFlow, Funtions Compute, Event Bridge | Kiy Deng | Approved for SIT and Dev only |  | Ang |  | HK DevOps | CloudFlow, Funtions Compute, Event Bridge are not in App requirement scope, please connect with Kenneth for approval
2025-07-29 | Zero Mu | IDass - Common Account | Dev, Test, Prod | ACK, ARMS,SLS,API GateWay, CloudFlow, Funtions Compute, Event Bridge | Eason Liu | Approved for SIT and Dev only |  | Ang |  | HK DevOps | CloudFlow, Funtions Compute, Event Bridge are not in App requirement scope, please connect with Kenneth for approval
2025-07-29 | Zero Mu | IDass - Common Account | Dev, Test, Prod | ACK, ARMS,SLS,API GateWay, CloudFlow, Funtions Compute, Event Bridge | Bocheng yang | Approved for SIT and Dev only |  | Ang |  | HK DevOps | CloudFlow, Funtions Compute, Event Bridge are not in App requirement scope, please connect with Kenneth for approval
2025-07-29 | Zero Mu | IDass - Common Account | Dev, Test, Prod | ACK, ARMS,SLS,API GateWay, CloudFlow, Funtions Compute, Event Bridge | Kenneth ng | Approved for SIT and Dev only |  | Ang |  | HK DevOps | CloudFlow, Funtions Compute, Event Bridge are not in App requirement scope, please connect with Kenneth for approval
2025-07-29 | Zero Mu | IDass - Common Account | Dev, Test, Prod | ACK, ARMS,SLS,API GateWay, CloudFlow, Funtions Compute, Event Bridge | Terence Leung | Approved for SIT and Dev only |  | Ang |  | HK DevOps | CloudFlow, Funtions Compute, Event Bridge are not in App requirement scope, please connect with Kenneth for approval
2025-08-05 | Kenneth Ng | IDass - Common Account(Jarvis) | Dev, Test, Prod | Read only - ADB, MongoDB, PolarDB, PostgreSQL, OSS, RocketMQ/RabbitMQ | Zero Mu | Approved for SIT and Dev only |  |  |  | HK DevOps
2025-08-05 | Kenneth Ng | IDass - Common Account(Jarvis) | Dev, Test, Prod | Read only - ADB, MongoDB, PolarDB, PostgreSQL, OSS, RocketMQ/RabbitMQ | Kiy Deng | Approved for SIT and Dev only |  |  |  | HK DevOps
2025-08-05 | Kenneth Ng | IDass - Common Account(Jarvis) | Dev, Test, Prod | Read only - ADB, MongoDB, PolarDB, PostgreSQL, OSS, RocketMQ/RabbitMQ | Eason Liu | Approved for SIT and Dev only |  |  |  | HK DevOps
2025-08-05 | Kenneth Ng | IDass - Common Account(Jarvis) | Dev, Test, Prod | Read only - ADB, MongoDB, PolarDB, PostgreSQL, OSS, RocketMQ/RabbitMQ | Bocheng yang | Approved for SIT and Dev only |  |  |  | HK DevOps
2025-08-05 | Kenneth Ng | IDass - Common Account(Jarvis) | Dev, Test, Prod | Read only - ADB, MongoDB, PolarDB, PostgreSQL, OSS, RocketMQ/RabbitMQ | Kenneth ng | Approved for SIT and Dev only |  |  |  | HK DevOps
2025-08-05 | Kenneth Ng | IDass - Common Account(Jarvis) | Dev, Test, Prod | Read only - ADB, MongoDB, PolarDB, PostgreSQL, OSS, RocketMQ/RabbitMQ | Terence Leung | Approved for SIT and Dev only |  |  |  | HK DevOps
2025-08-06 | Kenneth Lai | IDass - Common Account | Dev, Test | Model Studio, AI Guardrails | Edward Kan |  |  |  |  | Regional Asia Data Office team
2025-08-06 | Lamar Wei | IDass - Common Account | Dev, Test | ACK, PostgreSQL, OSS (R,W,X) | Zane Dai |  |  |  |  | DCS Project - CD IT
2025-08-06 | Lamar Wei | IDass - Common Account | Dev, Test | ACK, PostgreSQL, OSS (R,W,X) | Tanner Zhang |  |  |  |  | DCS Project - CD IT
2025-08-06 | Lamar Wei | IDass - Common Account | Dev, Test | ACK, PostgreSQL, OSS (R,W,X) | Lin Xu |  |  |  |  | DCS Project - CD IT
2025-08-06 | Lamar Wei | IDass - Common Account | Dev, Test | ACK, PostgreSQL, OSS (R,W,X) | Yancey Wu |  |  |  |  | DCS Project - CD IT
2025-08-06 | Lamar Wei | IDass - Common Account | Dev, Test | ACK, PostgreSQL, OSS (R,W,X) | Kiki Zeng |  |  |  |  | DCS Project - CD IT
2025-08-07 | Tiffany Guo | IDass - Common Account | DEV | ACK, ARMS, API GateWay, AliCloud portal, PolarDB, RDS for postgreSQL, RabbitMQ, KMS | Tiffany Guo |  |  | Ang | 2025-08-07
2025-08-07 | Arjay Nacion | IDass - Common Account | DEV | ACK, ARMS, API GateWay, AliCloud portal, PolarDB, RDS for postgreSQL, RabbitMQ, KMS | Arjay Nacion |  |  | Ang | 2025-08-07
2025-08-07 | Jonathan Quintal | IDass - Common Account | DEV | ACK, ARMS, API GateWay, AliCloud portal, PolarDB, RDS for postgreSQL, RabbitMQ, KMS | Jonathan Quintal |  |  | Ang | 2025-08-07
2025-08-07 | Eugene Alvizo | IDass - Common Account | DEV | ACK, ARMS, API GateWay, AliCloud portal, PolarDB, RDS for postgreSQL, RabbitMQ, KMS | Eugene Alvizo |  |  | Ang | 2025-08-07
2025-08-07 | Himanshu Sharmar | IDass - Common Account | DEV | ACK, ARMS, API GateWay, AliCloud portal, PolarDB, RDS for postgreSQL, RabbitMQ, KMS | Himanshu Sharmar |  |  | Ang | 2025-08-07
2025-08-26 | Darren Du | IDass - Common Account | Dev, Test | ACK, Model Studio, MongoDB, ADB | Dylan He
2025-08-26 | Darren Du | Trigger Build / Publish / Deploy Pipeline on Jenkins | Dev, Test | Jenkins (Azure) | Dylan He
2025-08-26 | Darren Du | IDass - Common Account | Dev, Test | ACK, Model Studio, MongoDB, ADB | Simon Yan
2025-08-26 | Darren Du | Trigger Build / Publish / Deploy Pipeline on Jenkins | Dev, Test | Jenkins (Azure) | Simon Yan
2025-08-26 | Darren Du | IDass - Common Account | Dev, Test | ACK, Model Studio, MongoDB, ADB | Bo Gou
2025-08-26 | Darren Du | Trigger Build / Publish / Deploy Pipeline on Jenkins | Dev, Test | Jenkins (Azure) | Bo Gou
2025-09-04 | Charles Ngo | Ali Model Studio - Account creation, Access | Dev, Test | Ali Model Studio | Jeremy Wu |  |  |  |  | Create Ali account for wujerem@mfcgd.com and grant access to the model studio in the workspace named mfc modelstudio-dev-uw
Notes:
This request covers only Dev and SIT environment. UAT and Prod access will follow new process (TBA)
Once completed the form please get approval from Aubrey Li （黎勉）

## HK Project by AliCloud Services
S.NO | Alicloud services | Group | #3: IDP Solution Jason Chan | #4: FUW (Future Underwriting Blueprint) ¦ GenAI Powered-up Underwriting Charles Ngo | #5: FUW (Future Underwriting Blueprint) ¦ One Single View NBUW Platform (NBUWS) Charles Ngo | CAS-MOD Ka Fai | #23: NBUW/FUW (Future Underwriting Blueprint) ¦ GenAI Powered-up Underwriting (For AA Team) - July Tech Launch Charles Ngo
1 | Model Studio (SG) - AI Guardrail - Qwen Max 2.5\LLM | AI Services | Y | Y | Y | N | Y
2 | ClousdSSO | Core - Identity |  | Y | Y | Y | Y
3 | IDaaS - Resource access management (RAM) | Core - Identity |  | Y | Y | Y | Y
4 | Infrastructure - NAT Gateway - Virtual private cloud (VPC) - ResourceManager - Cloud Config - Elastic IP (EIP) | Core - Infra |  | Y | Y | Y | Y
5 | Resource Orchestration Service (ROS) | Core - Infra |  | N | N | N | N
6 | Load Balancer - Application Load Balancer (ALB) - Network Load Balancer (NLB) - Server load balancer (SLB) | Core - Network |  | Y | Y | Y | Y
7 | Cloud DNS PrivateZone | Core - Network |  | Y | Y | Y | Y
8 | Cloud Enterprise Network (CEN) | Core - Network |  | Y | Y | Y | Y
9 | Cloud Firewall (CFW) | Core - Network |  | Y | Y | Y | Y
10 | Cloud Transit Router (TR) | Core - Network |  | Y | Y | Y | Y
11 | ExpressConnect | Core - Network |  | Y | Y | Y | Y
12 | Global Traffic Manager (GTM) | Core - Network |  | N | N | N | N
13 | Web Application Firewall (WAF) | Core - Network |  | N | N | N | N
14 | Elastic Compute Service (ECS) - Elastic Block Storage (EBS) | Core - Compute |  | Y | Y | N | Y
15 | ActionTrail | Core - Observability |  | Y | Y | Y | Y
16 | CloudMonitor | Core - Observability |  | Y | Y | Y | Y
17 | Application real time monitoring service (ARMS) - Grafana - Prometheus | Core - Observability | Y | Y | Y | Y | Y
18 | Function Compute (FC) | Core - Observability |  | Y | Y | N | Y
19 | Simple Log Service (SLS) | Core - Observability |  | Y | Y | Y | Y
20 | Anti-DDoS | Core - Security |  | N | N | N | N
21 | Data Security Center | Core - Security |  | N | N | N | N
22 | Apsara File Storage NAS (NAS) | Core - Storage |  | N | N | N | N
23 | Key management service (KMS) | Core - Storage | Y | Y | Y | Y | Y
24 | Object Storage Service (OSS) | Core - Storage | Y (on Day 15) | Y | Y | N | Y
25 | Hybrid Backup Recovery (Cloud Backup) | Core - Storage |  | Y | Y | Y | Y
26 | AnalyticsDB (ADB) | Database |  | Y | Y | N | Y
27 | ApsaraDB for MongoDB | Database | Y | Y | Y | N | Y
28 | ApsaraDB for Redis | Database |  | Y | Y | N | Y
29 | ApsaraDB RDS - ApsaraDB RDS for PostgreSQL - ApsaraDB RDS for SQL Server | Database |  | Y | Y (only PostgreSQL) | N | Y
30 | Data Management (DMS) | Database |  | N | N | N | N
31 | Data transmission service (DTS) | Database |  | N | N | Y | N
32 | EventBridge | Middleware | Y (on Day 15) | Y | Y | N | Y
33 | PolarDB | Database |  | Y | N | Y | Y
34 | DAS | Database |  | N | N | N | N
35 | Elastic Desktop Service (EDS/ Cloud PC) | End-user |  | Y | Y To confirm if Jarvis has it | N | Y
36 | ApsaraMQ - ApsaraMQ for Kafka - ApsaraMQ for RabbitMQ - ApsaraMQ for RocketMQ (TBC) | Message Queue | Y RocketMQ | Y | Y | N | Y
37 | API Gateway | Platform | Y | Y | Y | Y | Y
38 | Cloud Service Mesh | Platform |  | Y | Y | Y | Y
39 | Container Registry (ACR) | Platform |  | N | N | N | N
40 | Container Service for Kubernetes(ACK) | Platform | Y | Y | Y | Y | Y
41 | Dataworks | EDL |  | N | N | N | N
42 | MaxCompute | EDL |  | N | N | N | N
43 | Scheduler X | App |  | Y | Y | Y | Y
44 | CloudFlow (SG, Nov 2025 in HK) | Workflow |  | Y | Y | N | Y
45 | Flink | EDL |  | N | N | N | N
46 | Hologres | EDL |  | N | N | N | N
47 | PAI (for classification of image) |  | Y (on Day 15)
48 | Doc Parser |  | Y (on Day 15)
49 | PrivateLink |  | Y (on Day 15)
50 | Qwen Suite of Models ((Qwen-vl-max)) |  | Y
Note on H2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Qwen3-Max needed as well
Note on H27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AnalyticDB for PostgreSQL

## Ali Cloud Service
S.NO | Alicloud services | Group | Priority Set | DEV/SIT - Available Date | UAT - Available Date | PRD - Available Date | DCS (HK) Kelvin Chan | Jarvis (HK) Louis Tang | ATAS (GF) | Infor (GF) | ODS (HK) - TBD Michael Cheng | NBUW (HK) Charles Ngo | CAS (HK) Ka Fai | IRA Status | DEV/SIT Readiness | UAT Readiness | PRD Readiness | THR Readiness | THR WIP | ETS Comment
13 | Web Application Firewall (WAF) | Core - Network | 4 |  |  |  | N | N | N | N |  | N | N | N
19 | Simple Log Service (SLS) | Core - Observability | 2 |  |  |  | Y | Y | Y | Y |  | Y | Y | N |  |  |  | Completed | 12\13
43 | Scheduler X | App | 3 | 2025-09-15 | 2025-11-03 | 2026-01-05 | N | N | N | N |  | Y | Y | Can not be used in all env | N | N | N |  |  | Not Approved on AliCloud
5 | Resource Orchestration Service (ROS) | Core - Infra | 4 |  |  |  | N | N | N | N |  | N | N | N | Y | Y | Y | Requested
33 | PolarDB | Database | 1 | 2025-09-01 | 2025-10-01 | 2025-11-03 | N | N | N | N |  | Y | Y | Y |  |  |  | Completed | 6\21
47 | PA Firewall | Firewall | 1 | [10 empty] | N | Y | Y | Y | Completed | Completed
24 | Object Storage Service (OSS) | Core - Storage | 1 |  |  |  | Y | Y | Y | Y |  | Y | N | N |  |  |  | Completed | 9\22
50 | Model Studio (SG) - qwen3-vl-plus, qwen-vl-max, qwen-vl-max-0813, qwen3-vl-plus-2025-09-23 | AI Services | 2 |  |  |  | N | Y | N | N |  | Y | N | Can not be used in all env | N | N | N | <New Request> |  | AI need approval before using at AliCloud
1 | Model Studio (SG) - Qwen Max 2.5\LLM | AI Services | 2 |  |  |  | N | Y | N | N |  | Y | N | N | Y | Y | Y | Completed |  | new
49 | Model Studio (SG) - AI Guardrail | AI Services | 2 |  |  |  | N | Y | N | N |  | Y | N | N |  |  |  | Requested |  | new
42 | MaxCompute | EDL | 3 |  |  |  | N | N | Y | N |  | N | N | Y | Y | Y | N | <New Request> |  | IRA review needed on PRD
6 | Load Balancer - Application Load Balancer (ALB) - Network Load Balancer (NLB) - Classic load balancer (CLB) | Core - Network | 2 |  |  |  | Y | Y | Y | Y |  | Y | Y | N | Y | Y | Y | Completed
23 | Key management service (KMS) | Core - Storage | 1 |  |  |  | Y | Y | Y | Y |  | Y | Y | N |  |  |  | Completed | 19\19
4 | Infrastructure - NAT Gateway - Virtual private cloud (VPC) - ResourceManager - Cloud Config - Elastic IP (EIP) | Core - Infra | 1 |  |  |  | Y | Y | Y | Y |  | Y | Y | N | Y | Y | Y | Completed | 9\22
3 | IDaaS - Resource access management (RAM) | Core - Identity | 1 |  |  |  | Y | Y | Y | Y |  | Y | Y | N | Y | Y | Y | Completed | 16\16
25 | Hybrid Backup Recovery (Cloud Backup) | Core - Storage | 2 |  |  |  | Y | Y | N | Y | Y | Y | Y | N |  |  |  | Requested
46 | Hologres | EDL | 5 |  |  |  | N | N | N | N |  | N | N | N
12 | Global Traffic Manager (GTM) | Core - Network | 3 |  |  |  | N | N | N | N |  | N | N | N
18 | Function Compute (FC) | Core - Observability | 2 | 2025-09-01 | 2025-09-01 | 2025-10-01 | N | N | N | N |  | Y | N | N |  |  |  | Requested
45 | Flink | EDL | 5 |  |  |  | N | N | N | N |  | N | N | Y
11 | ExpressConnect | Core - Network | 1 |  |  |  | Y | Y | Y | Y |  | Y | Y | N | Y | Y | Y | Completed | 10\11
32 | EventBridge | Middleware | 2 | 2025-09-01 | 2025-09-01 | 2025-10-01 | N | N | N | N |  | Y | N | Y |  |  |  | Requested |  | Recheck with Kenneth
35 | Elastic Desktop Service (EDS/ Cloud PC) | End-user | 1 |  |  |  | N | N | N | N |  | Y | N | Y |  |  |  | Completed
14 | Elastic Compute Service (ECS) - Elastic Block Storage (EBS) | Core - Compute | 1 |  |  |  | N | N | N | Y |  | Y | N | N | Y | Y | Y | Completed | 18/18
41 | Dataworks | EDL | 3 |  |  |  | N | N | Y | N |  | N | N | Y | Y | Y | N | <New Request> |  | IRA review needed on PRD
31 | Data transmission service (DTS) | Database | 3 |  |  |  | N | N | N | N | Y | N | Y | Y |  |  |  | (Covered in DB)
21 | Data Security Center | Core - Security | 2 |  |  |  | N | N | N | Y |  | N | N | N
30 | Data Management (DMS) | Database | 4 |  |  |  | N | N | N | N |  | N | N | Y |  |  |  | (Covered in DB)
34 | DAS | Database | 5 |  |  |  | N | N | N | N |  | N | N | Y | [5 empty] | TBC
40 | Container Service for Kubernetes(ACK) | Platform | 2 |  |  |  | Y | Y | Y | N | Y | Y | Y | N | Y | Y | Y | Completed | 0/68
39 | Container Registry (ACR) | Platform | Reject |  |  |  | N | N | N | N |  | N | N | N |  |  |  | Not required |  | Use Artifactory
2 | ClousdSSO | Core - Identity | 1 |  |  |  | Y | Y | Y | Y |  | Y | Y | N | Y | Y | Y | Completed | 14\14
16 | CloudMonitor | Core - Observability | 2 |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y |  |  |  | <New Request>
44 | CloudFlow (SG, Nov 2025 in HK) | Workflow | 1 | 2025-09-01 | 2025-09-01 | 2025-10-01 | N | N | N | N |  | Y | N | N |  |  |  | Completed |  | new
10 | Cloud Transit Router (TR) | Core - Network | 1 |  |  |  | Y | Y | Y | Y |  | Y | Y | N | Y | Y | Y | Completed | 0\68
48 | Cloud Storage Gateway | Platform | 3 | [6 empty] | Y |  |  |  | Y |  |  |  | <New Request>
38 | Cloud Service Mesh | Platform | 2 |  |  |  | Y | Y | Y | N |  | Y | Y | N |  |  |  | Requested
9 | Cloud Firewall (CFW) | Core - Network | 2 |  |  |  | Y | Y | Y | Y |  | Y | Y | N | Y | Y | Y | Requested
8 | Cloud Enterprise Network (CEN) | Core - Network | 1 |  |  |  | Y | Y | Y | Y |  | Y | Y | N | Y | Y | Y | Completed | 16\16
7 | Cloud DNS PrivateZone | Core - Network | 1 |  |  |  | Y | Y | Y | Y |  | Y | Y | N | Y | Y | Y | Completed
36 | ApsaraMQ - ApsaraMQ for Kafka - ApsaraMQ for RabbitMQ - ApsaraMQ for RocketMQ | Message Queue | 2 |  |  |  | N | Y | Y | N |  | Y | N | N | Y | Y | Y | Completed
29 |  | Database | 1 |  |  |  | Y | Y | Y | N | Y | Y | N | N | Y | Y | Y | Completed
28 | ApsaraDB for Redis | Database | 1 |  |  |  | N | N | N | N |  | Y | N | N |  |  |  | Completed
27 | ApsaraDB for MongoDB | Database | 2 |  |  |  | N | Y | Y | N |  | Y | N | N | Y | Y | Y | Completed
22 | Apsara File Storage NAS (NAS) | Core - Storage | 5 |  |  |  | N | N | N | N |  | N | N | Y |  |  |  | Completed
17 | Application real time monitoring service (ARMS) - Grafana - Prometheus | Core - Observability | 2 |  |  |  | Y | Y | Y | Y | Y | Y | Y | N |  |  |  | Requested
37 | API Gateway | Platform | 2 |  |  |  | Y | Y | Y | N | Y | Y | Y | N | Y | Y | Y | Completed | 3\17
20 | Anti-DDoS | Core - Security | 4 |  |  |  | N | N | N | N |  | N | N | GCS
51 | AnalyticsDB (ADB) with Qwen3-Embedding-8B | AI Services | [11 empty] | N | N | N | N
26 | AnalyticsDB (ADB) | Database | 2 |  |  |  | N | Y | N | N |  | Y | N | N | Y | Y | Y | Completed
15 | ActionTrail | Core - Observability | 1 |  |  |  | Y | Y | Y | Y | Y | Y | Y | N | Y | Y | Y | Completed | 14/14
Column A-D are locked to prevent accidental update. Please connect with Dennis Mak if modification is required.
Notes:
SG - Production Requirement is to have "No internet facing and hardening(THR)" [hardening guideline could be provided by IRM team first before THR]
Note: If new Ali resource type is required. Please contact Kenneth Lai (HK Team) and Dennis Mak (ETS Team).
Priority reference
1 - Core foundation
2 - Compete before App go live (Prod) in Nov
3 - Complete before App go live (Prod) in Dec
4 - 5 - No use case
LLM Approval(https://mfc.sharepoint.com/sites/GDTSRGovernance/Lists/Foundation%20LLM%20Evaluation/AllItems.aspx?viewid=901da1ca%2Da1f1%2D44a7%2Da375%2D678527d2e039&e=OHcFh6&ovuser=5d3e2773%2De07f%2D4432%2Da630%2D1a0f68a28a05%2Clihelel%40MFCGD%2Ecom&OR=Teams%2DHL&CT=1753665454750&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNTA3MDMxODgwOSIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&CID=830cb6a1%2D1032%2D9000%2Dceed%2Dc49f271e9d9c&cidOR=SPO)
1 | Use case or Prompt Enginnering – needs MRM review by AA to make sure there is no security issue with privacy, data leakage and fairness etc(ADO and AA team)
2 | Foundation LLM Evaluation: The new foundation LLM must meet the benchmark on a predefined list of GenAI tasks established by the Global team(Eugene Wen, Global Data Technology )
| qwen3-vl-plus, qwen-vl-max, qwen-vl-max-0813, qwen3-vl-plus-2025-09-23 |  | LLM | LLM | 1) Base model approval: Process image: Ask Global AI Team what is the process for approval. Current playbook has no image task(Jonah)(ETA: 4 days)
| AnalyticsDB (ADB) with Qwen3-Embedding-8B |  | Embedded | Embedded | 2) ADO evalation(ETA:)
3) After approved before go live, use case of MRM approval is required . Some comparison with new model(some base model v4.1)(AI team will provide benchmark)(ETA:)
4) Archer is required involved busines( Regional - BUSO)(Business owner:Barry)(MAT)
|  |  | AI platform access |  | access to submit in SNow(AliCloud)
|  |  | AI platform test |  | POT to test new AI -> DEV -> SIT-> UAT-> PRD
*For evaluation on POT, we can only use synthetic or public data. Let's make sure this is true in case Global is providing new dataset for evaluating VL
qwen3-vl-plus, qwen-vl-max, qwen-vl-max-0813, qwen3-vl-plus-2025-09-23
| Step(LLM Approval managed by ADO) | Owner | Start | End | What | How | Readiness of VL: Cecilia: 20-Dec on UAT
| Base model review(Foundation LLM Capability Evaluation) | Jonah | 2025-11-18 | TBC |  | To confirm if additiional work required(Early next week)
| ADO evaluation(Platform) | Edward | 2025-11-18 | TBC
| Submit to ADO | Jonah
| Obtain Global Data Office(Vivian) | Edward
Enable of qwen3-vl-plus, qwen-vl-max, qwen-vl-max-0813, qwen3-vl-plus-2025-09-23
| Business to raise MAT for risk rating | Barry | 2025-11-18 | 2025-11-23 | MAT | Acceptanace Criteria
Use Case of MRM approval
| embedded model on DB | AnalyticsDB (ADB) with Qwen3-Embedding-8B |  |  |  | Edward to get clarify

## Followup
No | Date | Item | Details | Raised By | Status | Target Date | Handled By | Remarks
1 | 2025-07-21 | MFCGCR | waiting for dev and sit domain on Ali. (target July 31). cannot use IP to test AKS-> ACK (To be confirmed for MFCGCR, Derek Lau). 31 Jul - Workaournd (updateing the https host header) confirmed working ok by Louis, perm DNS forwarder will be impl 1 Aug 9pm HKT. | Kenneth | Closed | 2025-07-31 | Derek | Timeline to have AD go live(Workaround to setup local account for DEV) MFCGD forwarding will need to open at 3-Aug
2 | 2025-07-21 | Firewall | ACK to AKS firewall not open yet 1) AKS to ACK ALB - Firewall req submitted. (by 31 Jul) 2) ACK to AKS APIM - To built Egress on AliCloud and open firewall (by 31 Jul) | Kenneth Derek Elliott | Closed | 2025-07-31 | Derek | Working on firewall request and planned for tomorrow
3 | 2025-07-21 | ACK | ACK UAT env not available yet 1) UAT - 18 Aug ? (Requirement?) 2) Prod - | Kenneth | WIP | 2025-07-31 | Jeff | DEV and SIT are ready. UAT/PRD will discuss required date
4 | 2025-07-21 | Firewall | local env (from MFC, MT, Chendu offices) connect to Ali, need to open firewall ( Kenneth Lai, pls submit firewall and share the CHG number) (To provide more details for troubleshooting) | Kenneth | Closed | 2025-07-25 | Terry | RITM08768476 – HK and CD Office to Ali ALB (Dev, SIT) scheduled at 25-Jul-2025
5 | 2025-07-23 | Artifactory | To replace Ali ACR by Artifactory for deployment by 31-Jul. Allow ACR as temp work arround only in Dev. Delete ACR once Artifactory is ready | Elliott | Closed | 2025-07-31 | Raymond\Jomer | RITM08774687 will be implemented tomorrow
6 | 2025-08-06 | Production Support Access | OSS - how to control the permission on folder level, need allow support staff to view the content. Waiting Jeff Wang to share | Theresa | WIP | 2025-08-06 | Derek / Jeff | Lamer
7 | 2025-08-06 | Production Support Access | PostgreSQL- confirm how to do the setup for production support with read access on the specified tables in the database. As mentioned by Jeff, there is a blocker in Cyberark and Alicloud integration | Theresa | WIP | 2025-08-06 | Derek / Jeff | Lamer(non prod can use local admin)(UAT and PRD can be used in enxt week)
8 | 2025-08-06 | ACK | ACK DEV cannot connect DB and Redis | Theresa | Closed | 2025-08-06 | Derek | This is expected result due to egress control is enabled. Connected with Lamar and requested him to provide URL or required services for white list.
9 | 2025-08-12 | Gateway | DEV Gateway memory is limit to process LUA scripts to handle url re-write | Theresa | WIP | 2025-08-12 | Jeff / Ang | Cant display some pages(Lamar)

## Firewall
Opened | Env | Networkguardian # | RITM # | Description | Requester | Status | Remark
2025-08-12 | UAT | 1754898472875 | RITM08842844 | HK and CD VPN to access AliCloud ETS jumphost | Derek Lau | Completed
2025-08-12 | UAT | 1754897301509 | RITM08842843 | HK, CD Office to connect AliCloud ETS jump host | Derek Lau | Completed
2025-08-12 | UAT | 1754990918919 | RITM08854732 | Azure AKS Pod -> Ali ALB (ALB) | Marius Ramos | Completed
2025-08-12 | UAT | 1754994701206 | RITM08854650 | Ali ACK (Egress) to AKS APIM | Marius Ramos | Completed
2025-08-13 | UAT | 1755079023952 | RITM08854550 | ACK connect to DBs, MQ, Radis | Ang Gao | Completed
2025-08-13 | Dev | 1755065928746 | RITM08854548 | RSF Rabbit port5671 for VPN | Ang Gao | Completed
2025-08-13 | UAT | 1754982182042 | RITM08844351 | ACK Defender install | Ang Gao | Completed
2025-08-14 | UAT | 1755146079550 | RITM08851164 | Allow Alicloud UAT ACK cluster connect to Asia Artifactory | Raymond Li | Completed
2025-08-14 | UAT | 1755145381271 | RITM08850866 | Allow Asia Jenkins connect to Alicloud UAT ACK cluster | Raymond Li | Completed
2025-08-14 | UAT | 1755142481908 | RITM08854722 | Office (HK/CD) to ACK UAT API Server | Kenneth Ng | Completed
2025-08-14 | UAT | 1755144005525 | RITM08855093 | VPN (HK/CD) to ACK UAT API Server | Kenneth Ng | Completed
2025-08-14 | UAT | 1755144139863 | RITM08855096 | VPN (HK/CD) to ACK DEV API Server | Kenneth Ng | Completed
2025-08-14 | UAT | 1755144349393 | RITM08855107 | VPN (HK/CD) to ACK SIT API Server | Kenneth Ng | Completed
2025-08-14 | SIT | 1755141026251 | RITM08854591 | CD Office to connect AliCloud Mongo DB | Euphonia Fung | Completed
2025-08-14 | Dev | 1754982639623 | RITM08846467 | CD Office to connect AliCloud Mongo DB | Euphonia Fung | Completed
2025-08-14 | UAT | 1755159386445 | RITM08854618 | Office (HK, CD) to connect ACK via ALB | Kenneth Ng | Completed
2025-08-14 | UAT | 1755159811552 | RITM08855298 | VPN (HK, CD) to connect ACK via ALB | Kenneth Ng | Completed
2025-08-18 | Dev | 1755503275563 | RITM08861988 | Dev ACK egress Target: Ali LLM VPC | Darren Du | Completed
2025-08-19 | Dev | 1755597047640 | RITM08874673 | MAC VPN (HK) to Jumphost, RSF resources | Derek Lau | Completed
2025-08-20 | Prod | 1755681842776 | RITM08870739 | Ali (All subnet) to Defender endpoint | Derek Lau | Completed
2025-08-26 | Dev | 1756112068485 | RITM08894845 | ACK(Dev) to connect to ADB (Database + Embedding AI) | Lee Li | Completed
2025-08-26 | Dev | 1756110788055 | RITM08894853 | Office (HK, CD) to connect ADB (Dev) | Lee Li | Completed
2025-08-26 | Dev | 1756111040607 | RITM08894540 | VPN (HK, CD) to connect ADB (Dev) | Lee Li | Completed
2025-08-26 | Dev | 1756116206484 | RITM08893390 | Office & VPN (HK, CD) to connect LLM (Dev) | Lee Li | Completed
2025-08-20 | SIT | 1755599374930 | RITM08870037 | HK/HK VPN/CD VPN to connect MongoDB | Euphonia Fung | Completed
2025-08-20 | DEV | 1755598795883 | RITM08870031 | HK/HK VPN/CD VPN to connect MongoDB | Euphonia Fung | Completed
2025-08-26 | Prod | 1756195060383 | RITM08893796 | Ali Env -> Ali Repo Server | Johnny Wang | Completed
2025-08-26 | Prod | 1756190906258 | RITM08889369 | Office, VPN (HK,CD, MAC) -> Ali Repo Server | Johnny Wang | Completed
2025-08-26 | Prod | 1756195385015 | RITM08893795 | Ali WSUS server -> Microsoft URL | Johnny Wang | Completed
|  |  | RITM08894254 | VDI to RDS DEV, SIT, UAT | Lee Li | Completed | DCS
|  |  | RITM08893659 | ack(dev/sit/uat) to Azure (login.microsoftonline.com) | Lee Li | Completed | DCS
|  |  | RITM08878628 | ADF[AZWAPNHKNGEDL01] to Azure key vault[https://mfcakveasdcsdev01.vault.azure.net/] | Lee Li | Completed
|  |  | RITM08874874 | CA CLIENT SERVER[azwdbnhisats01] to API GW(UAT)[10.83.130.83, 10.83.129.156]) | Lee Li | Completed | DCS
|  |  | RITM08873976 | Office¦VPN to RDS(UAT)[pgm-3nsu6wy96z5zqm88.pg.cnhk.rds.aliyuncs.com]) | Lee Li | Completed | DCS
|  |  | RITM08873954 | Jenkins to RDS UAT[pgm-3nsu6wy96z5zqm88.pg.cnhk.rds.aliyuncs.com]) | Lee Li | Completed | DCS
|  |  | RITM08873982 | ADF[AZWAPNHKNGEDL01] to RDS(UAT)[pgm-3nsu6wy96z5zqm88.pg.cnhk.rds.aliyuncs.com]) | Lee Li | Completed | DCS
|  | 1756274074600 |  | VDI to Ali ALB DEV/SIT/UAT | Lee Li | Completed | DCS
|  | 1756262636025 |  | Ali ACK[UAT] egress to Azure Blob[mfcblobadouateas01.blob.core.windows.net] | Lee Li | Completed | DCS
|  |  | RITM08878628 | ADF[AZWAPNHKNGEDL01] to Azure key vault[https://mfcakveasdcsdev01.vault.azure.net/] | Lee Li | Completed | DCS
|  |  | RITM08874874 | CA CLIENT SERVER(AZWDBNHISATS01) to UAT ALB(10.83.130.83、10.83.129.156) | Lee Li | Completed | DCS
|  |  | RITM08837962 | Jenkins to RDS sit [pgm-3ns4w4l10xolewgr.pg.rds.aliyuncs.com] | Lee Li | Completed | DCS
|  |  | RITM08838303 | CA CLIENT SERVER[azwdbnhisats01] to Azure key vault[https://mfcakveasdcsdev01.vault.azure.net/] | Lee Li | Completed | DCS
|  |  | RITM08837863 | CA CLIENT SERVER[azwdbnhisats01] to Azure key vault[https://mfcakv-eas-edlhk-nprd-01.vault.azure.net、https://mfcakv-eas-edlhk-nprd-02.vault.azure.net] | Lee Li | Completed | DCS
|  |  | RITM08803020 | ADF[AZWAPNHKNGEDL01] to RDS dev [pgm-3nso8s3z962om101.pg.rds.aliyuncs.com] | Lee Li | Completed | DCS
|  |  | RITM08759882 | Jenkins to RDS dev [pgm-3nso8s3z962om101.pg.rds.aliyuncs.com] | Lee Li | Completed | DCS
|  |  | RITM08737658 | VPN to RDS dev [pgm-3nso8s3z962om101.pg.rds.aliyuncs.com] | Lee Li | Completed | DCS
|  |  | RITM08728699 | ADF[AZWAPNHKNGEDL01] to API GW dev[10.83.200.41, 10.83.199.51] | Lee Li | Completed | DCS
|  |  | RITM08728706 | CA SERVER AGENT to API GW dev[10.83.200.41, 10.83.199.51] | Lee Li | Completed | DCS
|  |  | RITM08728726 | Azure->API GW dev[10.83.200.41, 10.83.199.51] | Lee Li | Completed | DCS
|  |  | RITM08699620 | Azure->API GW sit[10.83.199.48, 10.83.200.38] | Lee Li | Completed | DCS
|  |  | RITM08728733 | VPN to API GW dev[10.83.200.41, 10.83.199.51] | Lee Li | Completed | DCS
|  |  | RITM08699624 | ADF[AZWAPNHKNGEDL01] to API GW sit[10.83.199.48, 10.83.200.38] | Lee Li | Completed | DCS
|  |  | RITM08699618 | VPN to API GW sit[10.83.199.48, 10.83.200.38] | Lee Li | Completed | DCS
|  |  | RITM08699612 | CA SERVER AGENT to API GW dev[10.83.199.48, 10.83.200.38] | Lee Li | Completed | DCS
|  |  | RITM08699622 | ADF[AZWAPNHKNGEDL01] to RDS dev [pgm-3ns4w4l10xolewgr.pg.rds.aliyuncs.com] | Lee Li | Completed | DCS
2025-07-10 | DEV | 1751528064153 | RITM08708332 | jenkins to ACR | Zero Mu | Completed
2025-08-27 | DEV | 1756285802419 |  | ACK to Eventbridge | Jason Peng | Completed | NB
2025-08-27 | DEV | 1756288879161 |  | AKS DEV to HK STS token | Jason Peng | Completed | NB
2025-08-27 | SIT | 1756289316010 |  | AKS SIT to HK STS token |  | Completed
2025-08-27 | UAT | 1756289510174 |  | AKS UAT to HK STS token |  | Completed
| DEV |  | RITM08798315 | AKS to Cloudflow SG | Jason Peng | Completed | NB
2025-08-29 | UAT | 1756433535684 | RITM08909262 | CD/HK office connect to LLM VPC | Darren Du | Completed
2025-08-29 | UAT | 1756433887554 |  | CD/HK VPN office connect to LLM VPC | Darren Du | Completed
2025-08-29 | UAT | 1756434089906 | RITM08909301 | CD/HK office connect to ADB | Darren Du | Completed
2025-08-29 | UAT | 1756434275020 | RITM08909308 | CD/HK VPN office connect to ADB VPC | Darren Du | Completed
2025-08-29 | UAT | 1756434442329 | RITM08909335 | ACK connect to LLM | Darren Du | Completed
2025-08-29 | UAT | 1756434828069 | RITM08909337 | ACK connect to ADB | Darren Du | Completed
2025-08-29 | UAT | 1756435011697 | RITM08909340 | ACK connect to ADB (Embedding AI) | Darren Du | Completed
2025-08-29 | UAT | 1756435621500 | RITM08909704 | ACK connect to mongodb | Darren Du | Completed
2025-08-29 | NonProd+Prod | 1756289012626 | RITM08903505 | Ali (All subnet) to Defender endpoint (Additional EU URLs) | Derek Lau | Completed
2025-09-01 | NonProd+Prod | 1756697060883 | RITM08910788 | MAC VPN (HK GW) to Grafana Dashboard | Derek Lau | Completed
2025-09-01 | NonProd+Prod | 1756697602875 | RITM08910797 | RSF AVD to Grafana Dashboard | Derek Lau | Completed
2025-09-01 | DEV | 1756705521000 | RITM08708332 | CD/HK Office and VPN connect to RDS DEV [pgm-3ns82nx4z5f92195.pg.cnhk.rds.aliyuncs.com] | Zero Mu | Completed
|  |  | RITM08918569 | ACK to RDS, KMS, RabbitMQ (RSF DEV) | Arjay Nacion | Completed
2025-09-03 | UAT | 1756895939878 | RITM08929390 | ACK to ADB AI Embedding | Darren Du | Completed
2025-09-04 | DEV | 1756980361685 | RITM08929374 | ACK to ADB AI Embedding (Change new URL) | Darren Du | Completed
2025-08-29 | UAT | 1756345778083 | RITM08899940 | CD/HK office connect to MongoDB | Darren Du | Completed | Jarvis
2025-09-15 | DEV | 1757923824234 | RITM08973523 | RSF - Azure RSF cluster (aks-eas-yoda-cluster) to Alicloud RSF ACK cluster | Derek Lau | Completed | RSF
2025-09-19 | Prod | 1758185587257 | RITM08979330 | Jenkins to RDS | Lee Li
2025-09-19 | Prod | 1758185219004 | RITM08979321 |  | Lee Li
2025-09-19 | Prod | 1758183101513 | RITM08979324 |  | Lee Li
2025-09-23 | Prod | 1758162589930 | RITM08984656 | CD&HK VPN: Firewall settings for connecting to Alibaba Cloud | Ethan Cao | Completed
2025-09-23 | Prod | 1758105291068 | RITM08993272 | ACK egress traffic to Alibaba Cloud ADB AI Gateway. | Ethan Cao | Completed
2025-09-23 | Prod | 1758104655010 | RITM08984683 | ACK Egress Subnet connects to the MongoDB instance on Alibaba Cloud. | Ethan Cao | Completed
2025-09-23 | Prod | 1758104400073 | RITM08993270 | ACK Egress traffic to Alibaba Cloud Redis instance | Ethan Cao | Completed
2025-09-23 | Prod | 1758105103647 | RITM08984641 | ACK Egress traffic will be routed to Alibaba Cloud's ADB-Jarvis service. | Ethan Cao | Completed
2025-09-23 | Prod | 1758104896765 | RITM08984547 | ACK Egress to Alibaba Cloud's RocketMQ. | Ethan Cao | Completed
2025-09-23 | Prod | 1758505782165 | RITM08984547 | ACK Node subnet to Prisma Cloud (Public) | Ethan Cao | Completed
2025-09-23 | Prod | 1758172817892 | RITM08989114 | ACK Production Environment Firewall Configuration Request (prior to deployment on Alibaba Cloud) | Ethan Cao | Completed
2025-09-23 | Prod | 1758159621156 | RITM08984908 | Enable firewall for Jenkins to access the Alibaba Cloud API server. | Ethan Cao | Completed
2025-09-23 | Prod | 1758100919028 | RITM08984728 | ACK Egress Subnet to Alibaba Cloud Firewall. | Ethan Cao | Completed
2025-09-23 | Prod | 1758162070406 | RITM08984694 | Enable firewall for connections between CD&HK Office and Alibaba Cloud. | Ethan Cao | Completed
2025-09-23 | Prod | 1758161052255 |  | Configuration of ACK egress firewall rules for the production environment to access resources on Alibaba Cloud | Ethan Cao | Imp 25 Sep
2025-09-25 | Prod | 1758784361751 | RITM08998167 | Azure AKS Pod -> Ali ALB (ALB) | Marius Ramos | Completed
2025-09-25 | Prod | 1758784164449 | RITM08998237 | Ali ACK (Egress) to Azure AKS APIM SEA | Marius Ramos | Completed
2025-09-26 | Prod | 1758784164449 | RITM08998237 | Ali ACK (Egress) to Azure AKS APIM EAS | Marius Ramos | Completed
2025-10-02 | Prod | 1759396866333 |  | Office (HK/CD) to ACK PROD API Server | Kenneth Ng
2025-10-02 | Prod | 1759397837496 |  | VPN (HK/CD) to ACK PROD API Server | Kenneth Ng
2025-10-02 | Prod | 1759398213304 |  | Office (HK, CD) to connect ACK via ALB PROD | Kenneth Ng
2025-10-02 | Prod | 1759398324559 |  | VPN (HK, CD) to connect ACK via ALB PROD | Kenneth Ng

## THR(OLD) (hidden)
THR | Status | THR(https://mfc.sharepoint.com/:l:/r/sites/GDTSRGovernance/Lists/Foundation%20LLM%20Evaluation?e=OHcFh6)
Apsara RocketMQ | Not yet approved
Apsara RDS PostgreSQL | THR
Apsara Redis | Requested
Container Registry(ACR Service) | Requested | replaced by Artifactory\Jenkins | Not required
SLS | THR
ACK | THR |  | Jarvis
API gateway | Requested
ALB – Requested | Requested
Analytic DB | Not yet requested
Qwen Max 2.5\LLM | THR | Model Studio | Jarvis
ADB | approved by IRM | New company approval | Jarvis
AI Guardrail | waiting by IRM |  | Jarvis
Cloud Service Mesh | Requested
Dataworks | Requested
ApsaraMQ for Kafka | Requested
Data Security Center | Requested
Cloud Firewall (CFW) | Requested

## THR
THR | Status | THR(https://mfc.sharepoint.com/:l:/r/sites/GDTSRGovernance/Lists/Foundation%20LLM%20Evaluation?e=OHcFh6)
ACK | THR
ActionTrail
ADB | approved by IRM | New company approval
AI Guardrail | waiting by IRM |  | Not required
ALB – Requested | Requested
Analytic DB | Not yet requested |  | Jarvis
AnalyticsDB (ADB)
API gateway | Requested
API Gateway
Application real time monitoring service (ARMS) |  |  | Jarvis
Apsara RDS PostgreSQL | THR |  | Jarvis
Apsara Redis | Requested |  | Jarvis
Apsara RocketMQ | Not yet approved
ApsaraDB for MongoDB
ApsaraDB RDS - ApsaraDB RDS for PostgreSQL - ApsaraDB RDS for SQL Server
ApsaraMQ for Kafka | Requested
ApsaraMQ - ApsaraMQ for RabbitMQ - ApsaraMQ for RocketMQ
Cloud DNS PrivateZone
Cloud Enterprise Network (CEN)
Cloud Firewall (CFW) | Requested
Cloud Service Mesh | Requested
Cloud Transit Router (TR)
CloudMonitor
ClousdSSO
Container Registry(ACR Service) | Requested | replaced by Artifactory\Jenkins
Container Service for Kubernetes(ACK)
Data Security Center | Requested
Dataworks | Requested
Elastic IP (EIP)
ExpressConnect
Grafana
Hybrid Backup Recovery (Cloud Backup)
IDaaS
Key management service (KMS)
Load Balancer - Application Load Balancer (ALB) - Network Load Balancer (NLB) - Server load balancer (SLB)
NAT Gateway
Object Storage Service (OSS)
Qwen Max 2.5\LLM | THR | Model Studio
Resource access management (RAM)
SLS | THR
Virtual private cloud (VPC)

## AliCloud_Azure_mapping
Alibaba Cloud Service | Code | Azure Services Equivalent
Alibaba Cloud DNS PrivateZone |  | Azure Private DNS
Alibaba Cloud Model Studio |  | Azure AI Studio / Azure Machine Learning
AnalyticDB for PostgreSQL |  | Azure Synapse Analytics + Azure Database for PostgreSQL
API Gateway |  | Azure API Management
Application Real-Time Monitoring Service | ARMS | Azure Monitor + Application Insights
ApsaraDB for MongoDB |  | Azure Cosmos DB for MongoDB
ApsaraDB RDS |  | Azure Database (MySQL/PostgreSQL/MariaDB) / Azure SQL
ApsaraMQ |  | Azure Event Hubs / Azure Service Bus
Certificate Management Service |  | Azure Key Vault Certificates
Cloud Backup |  | Azure Backup
Cloud Data Transfer |  | Azure Data Box / Azure Data Factory
Cloud Firewall |  | Azure Firewall
Cloud Monitor |  | Azure Monitor
Cloud Storage Gateway |  | Azure File Sync / Azure StorSimple (legacy)
Container Registry |  | Azure Container Registry
Container Service for Kubernetes | ACK | Azure Kubernetes Service (AKS)
Data Management | DMS | Azure Data Studio / Azure Database tools
Data Security Center |  | Microsoft Purview
Data Transmission Service | DTS | Azure Database Migration Service / Azure Data Factory
Database Autonomy Service | DAS | Azure SQL Intelligent Performance / Azure Automanage
DataWorks |  | Azure Synapse Pipelines / Azure Data Factory
Elastic Block Storage | EBS | Azure Managed Disks
Elastic Compute Service | ECS | Azure Virtual Machines
Elastic Desktop Service Enterprise | EDS | Azure Virtual Desktop
Elastic IP Address |  | Azure Public IP Address
Express Connect |  | Azure ExpressRoute
Function Compute |  | Azure Functions
Identity as a Service | IDaaS | Microsoft Entra ID
Key Management Service | KMS | Azure Key Vault
Marketplace |  | Azure Marketplace
MaxCompute |  | Azure Synapse Analytics (Big Data / Data Warehouse)
Microservices Engine | MSE | Azure Service Fabric / Dapr on AKS
NAT Gateway |  | Azure NAT Gateway
Object Storage Service | OSS | Azure Blob Storage
Open Search |  | Azure AI Search
PolarDB |  | Azure Database for PostgreSQL/MySQL / Azure SQL Hyperscale
PrivateLink |  | Azure Private Link
Realtime Compute for Apache Flink |  | Azure Stream Analytics / Azure HDInsight Flink
Server Load Balancer | SLB | Azure Load Balancer / Azure Application Gateway
Service Mesh |  | Open Service Mesh on AKS
Simple Log Service | SLS | Azure Monitor Logs / Log Analytics
Tair (Redis OSS-compatible) |  | Azure Cache for Redis
Virtual Private Cloud | VPC | Azure Virtual Network (VNet)

## Agile (hidden)
August Deliverables | 4-Aug to 8-Aug | 11-Aug to 15-Aug | 18-Aug to 22-Aug | 25-Aug to 29-Aug | User Access | Development | Produciton Support | THR or start of test
DCS(Theresa) | To fully test on DEV |  |  |  | User Access: MFCGD Entra ID | Developer: MFCGCR Entra ID or Ali SSO account | Production support team: MFCGCR Cyberarc or Ali SSO account(no Cyberark)*MFCGCR can store at Ali | THR or new service: No production data and can use on non-production only
Jarvis(Louis) | To fully test on DEV ACK to AKS tested Logging and monitoring: not tested | i) 15-Aug- UAT testing ii) ADB will need to approve to use at UAT |  |  | User Access: MFCGD Entra ID and O365HK Agency Entra ID | Developer: MFCGCR Entra ID or Ali SSO account | Production support team: MFCGCR Cyberarc or Ali SSO account(no Cyberark)*MFCGCR can store at Ali | THR or new service: No production data and can use on non-production only
Jenkins\Artifactory | Normal support
MCF\RCF(End of Sep)
DevSecOps | CI\CD for HK is completed(to shutdown ACR) PH support to access to AliCloud | To start normal support - AliCloud ACK Cluster - KMS instance - RabbitMQ instance - API gateway - Polar DB instance - Adminstractive level access on API gateway
AD | Local account for DEV and MFCGCR for others | To setup group | Ready to create AD account
Current Week | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08
DCS | Testing is in progress and can see front page | LUA script to re-direct App Penetration Test(connectivity to vendor - should not - Theresa to confirm) | C2L log(OSS required) Log to Sentinel(Derek to provide on Ali logging and provided by Theresa) Log for Apps only(to OSS only for apps checking)(apps requirement by Theresa to Derek)
Jarvis | i) ACK to ASK tested (DEV and SIT are good) ii) ADB is testing on DEV and SIT | Logging and monitoring: not tested
Jenkins\Artifactory | Normal support
MCF(End of Sep)
DevSecOps (Utility server at Azure-HK in future; AVD at HK currently) | i) Login provided. ii) Trying the access from PH to Ali(all resource) iii) VPN access is applying iv) Approval raised ACK to Artifactory\Jenkin(CI\CD pipeline) | Login test(Jonathan Quintal) |  | Opening firewall for ACK to Artifactory\Jenkin(CI\CD pipeline)(1753772006933 1753699458814) | To start work normally after 8-Aug
AD | To prepare group and user | To submit group and user for IRM approval | i) Handover of AD to ETS-Asia ii) Resource: MSL | To prepare KT and procedure documents | To prepare KT and procedure documents Ready for production setup
| Timeline | Work
| Current | To confirm infra access and account design
| 2025-08-08 | To have account design reviewed with IRM
| 2025-08-08 | Start UAT Cluster creation
| 2025-08-12 | UAT Cluster created
| 2025-08-14 | Firewall open to UAT Cluster
| 2025-08-15 | Testing of UAT Cluster and release UAT to HK

## GCR_Global Standard (hidden)
Type | Current Global Standards
CyberArk | No change
WAF (Akamai) | No Change
Endpoint Detection (Defender(e5), Tanium(no mfcgd)) | No Change
Certificates and secret Management | No Change
Data Classification (Purview) | Before Prod
Hardening Management (THR) | No Change
Vulnerability Management (Qualys) | No Change
DevSec Ops Security (CWP) | n/a
Security Center/ Compliance - CSPM | n/a
Logging - Action Trail, Simple Log Services, Logtail, SIEM (ADX) | No Change
Monitoring - OpenTelemetry, Grafana, ARMS, Prometheus | Enable monitoring for ACK Dev. Request for Endorsement from monitoring team/ Global & HK.
Monitoring - Alerting intergration with Moosoft | No Change
Asset Management(SNow) | No Change
VPN Access(Cisco Secure Client) | No Change
User Internet Policy Control(Zscaler) | No Change
Internet Inbound & Outbound(PA) | No Change
Private\Public DNS(Manulife) | No Change
Active Directlry and Identity(EntraID & AD) | No Change
Schedule(CA)(*Apps Responsibility to setup) | No Change

## BAU (hidden)
No | Task | What | Who
1 | On board | CI created in SNow | New service owners
2 | On board | Cyberark | New service owners
x

## IRA (hidden)
Network Security [Joey] |  |  |  |  | Response\Followup Action
East West Firewall (Cross VPC)
|  | Permissive rules |  |  | Started in UAT Cluster
NSG
|  | Permissive rules |  |  | Started in UAT Cluster
PA firewall (North South Firewall)
|  | # of resource in DMZ subnet (EIP detail) |  |  | NAT gateway whitelist and chagne to outbound to PA at Sep
TCP port scan result by Qualys (should only 443)
Permissive rules
|  | All inbound rules are from akamai |  |  | PA firewall at Sep
Akamai
Authentication
# of SSO account
|  | Vendor |  |  | MFA and Cyberark
MFA turn on
Cyberark
# of RAM account
interactive login
|  | non-interactive login |  |  | AKS
Password policy
# of AKSK created and expiration date
Authorization [Aubrey]
Approval
|  | #of approval vs # of new role assignment |  |  | IRM approval
Roles
|  | List of Cloudadmin (admin) |  |  | IRM approval
|  | List of diff type of roles and assignment to users |  |  | IRM approval
| Roles assignment assign to user group but not user |  |  |  | IRM approval
| User group need to have an indication for privilege group and reviewed through IIQ |  |  |  | Ali Process to be defined
Admin Tool Protection [Edison][Alan]
|  | IP restriction | Device restriction
| portal | Y | N
| CLI | N | N | Should raise a CAP
| SDK | N | N
| Restapi | N | N
Logging and Monitoring[][Alan\Derek]
|  | OSS | ECS | … (36 Cloud Services)
#
| SLS |  |  |  | Monitoring - Granfana(ali) opened and have 2 dashboards
| ADX |  |  |  | Setinel - Windows\Linux\Action Trail(applied), Other- ?, App log - ?
Encryption for data in transit and at rest[Alan]
Control policy existence
| Control policy exception |  |  |  | Public - cant access
Data Location/Residency
# of resource in regions outside of HK (Should be null except SG Qwen)
Existence of policy to restrcit resources created outside of HK
Vulnerability Management (Hardening, Patching, Anti-ware, Pen-test)
| Hardening |  | [Either Nizam team or Us][GCS]
|  |  | THR exist? | Hardening complete by operation team? (Fill by Alan) Ali native CSPM policy tuning Ali native CSPM findings Prisma CSPM policy creation/tuning Prisma CSPM finding Prisma CWP (For ACK)
ACK (Need large effort)
OSS
# of Bucket vs # of bucket policy
ECS
… (36 Cloud Services)
Patching
Patching tool availability (e.g. ansible agent)
Qualys agents in ECS?
Qualys findings show up in Qualys console
Qualys monitoring [PTG]
Anti-malware
|  |  | Can see in console? (ECS) | #of ECS vs # of items in console
defender
tanium
Pentest [GCS]
To complete before go live (~Nov)
Asset Management [GCS]
| CMDB alicloud items vs actual resrouces in alicloud |  |  |  | Queue created for Ali Support CI created - VM Service Request flow - To be created Tagging - WIP
Data Leakage Prevention
Domain Controller
check the list of users in all the admin goups